## Sheet1
a) Order Number | b) Program | c) Circuit ID Number | d) Circuit-Segment ID | e) Wildfire Risk Score Post-mitigation | e2) Wildfire Risk Score Pre-mitigation | f) Expected/Actual Start Date | g) Expected Completion Date | h) Length of CC to be Installed (Circuit Miles) | i) Length of SUG conductor to be installed in 2025 | j) Length of OH Conductor Permanent Removed in 2025 replaced with SUG (Circuit Miles) | k) Length of OH Conductor Permanent Removed in 2025 replaced with CC (Circuit Miles) | l) Length of Bare Wire Install in 2024 | m) Length of Bare Wire Install in 2025 | Total Customers | Minutes of PSPS Outage by Circuit
0441-DUG-A-SUG | SUG | C0441 | 441-23R | 0.00036495 | 0.00072605 | 2024-05-23 | 2025-02-11 |  | 6.12 | 4.65 |  |  |  | 75 | 23270
0220-U-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2024-07-26 | 2025-01-08 | 0 | 3.02 | 2.3 |  | 0 | 0 | 132 | 20222
0222-B-SUG | SUG | C0222 | 222-1364R | 0.000985 | 0.0045724 | 2024-07-29 | 2025-01-17 | 0 | 3.8 |  |  | 0 | 0 | 438 | 37264
0217-A-SUG | SUG | C0217 | 217-983R | 0 | 0.0029499 | 2024-08-05 | 2025-01-16 | 0 | 3.3 |  |  | 0 | 0 | 78 | 13132
0217-B-SUG | SUG | C0217 | 217-983R | 0 | 0.0029499 | 2024-08-09 | 2025-03-10 | 0 | 3.7 |  |  | 0 | 0 | 78 | 13132
0442-DUG-SUG | SUG | C0442 | 442-729 |  |  | 2024-08-09 | 2025-04-22 | 0 | 6.2 | 1.59 |  | 0 | 0 | 1137 | 13500
0445-G-SUG | SUG | C0445 | 445-1311R | 0.00054182 | 0.001547 | 2024-08-16 | 2025-03-17 | 0 | 4.12 | 2.88 |  | 0 | 0 | 179 | 28176
0220-W-SUG | SUG | C0220 | 220-288R | 0 | 0.00013367 | 2024-09-16 | 2025-01-10 | 0 | 2.04 |  |  | 0 | 0 | 261 | 20222
0220-N-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2024-10-07 | 2025-03-19 | 0 | 3.5 | 1.12 |  | 0 | 0 | 132 | 20222
0222-FF-SUG | SUG | C0222 | 222-2013R | 0.0010472 | 0.0014909 | 2024-10-09 | 2025-04-15 | 0 | 4.18 |  |  | 0 | 0 | 245 | 37264
0520-E-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2024-10-17 | 2025-01-14 | 1.0604 |  |  |  |  | 0 | 267 | 3982
0075-A-CC | CC | C0075 | 75-996R, CB 91 | 2.3879e-05 | 3.9133e-05 | 2024-10-22 | 2025-01-19 | 0.32083 |  |  |  |  | 0 | 1738 | 15147
0220-S-SUG | SUG | C0220 | 220-298R | 0.00065801 | 0.0018868 | 2024-10-23 | 2025-05-21 | 0 | 4.2 | 2.81 |  | 0 | 0 | 132 | 20222
0350-F-CC | CC | C0350 | 350-2196R | 8.928e-05 | 0.00015059 | 2024-10-25 | 2025-01-22 | 1.4571 |  |  |  |  | 0 | 238 | NA
0222-T-SUG | SUG | C0222 | 222-1401R | 8.4956e-06 | 0.006763 | 2024-10-30 | 2025-02-25 | 0 | 1.73 | 1.94 |  | 0 | 0 | 260 | 37264
0073-CC-CC | CC | C0073 | 73-1130 | 0.00025314 | 0.00058691 | 2024-11-07 | 2025-02-04 | 0.60966 |  |  |  |  | 0 | 144 | 14052
0222-K-SUG | SUG | C0222 | 222-1503, 222-2013R | 0.0010472 | 0.0014909 | 2024-11-12 | 2025-02-14 | 0 | 3.18 |  |  | 0 | 0 | 287 | 37264
0520-A-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2024-11-13 | 2025-02-10 | 1.3078 |  |  |  |  | 0 | 267 | 3982
0210-G-SUG | SUG | C0210 | 210-9R | 0 | 6.4591e-05 | 2024-11-26 | 2025-03-24 | 0 | 2.7 | 1.8 |  | 0 | 0 | 190 | 3338
0520-B-CC | CC | C0520 | 520-1489R | 4.4457e-05 | 6.4177e-05 | 2024-11-27 | 2025-02-24 | 1.2658 |  |  |  |  | 0 | 267 | 3982
0221-B-SUG | SUG | C0221 | 221-37AE | 0.00023319 | 0.00026009 | 2024-12-05 | 2025-06-24 | 0 | 5 |  |  | 0 | 0 | 915 | 23206
0210-N-SUG | SUG | C0210 | 210-9R | 0 | 6.4591e-05 | 2024-12-27 | 2025-04-21 | 0 | 3.6 |  |  | 0 | 0 | 190 | 3338
0210-C-SUG | SUG | C0210 | 210-172R | 0 | 0.00027968 | 2024-12-30 | 2025-02-20 | 0 | 0.5 | 0.19 |  | 0 | 0 | 213 | 3338

## Final
b) Program | SUG
Circuit Segment | Count of d) Circuit-Segment ID | Max of Total Customers | Sum of i) Length of SUG conductor to be installed in 2025 | Max of Minutes of PSPS Outage by Circuit | Length (mi) | Cost | Customers | PSPS Circuit Minutes | Cost/Customer | Off Grid $60k | OG Costs | Customer minutes | PSPS Cost per customer minute | Log cpcm | Bins | Binned cost
210-172R | 1 | 213 | 0.5 | 3338 | 0.5 | 1500000 | 213 | 3338 | 7042.2535 |  | 1500000 | 710994 | 2.1097 | 0.32423 |  | 0
210-9R | 2 | 190 | 6.3 | 3338 | 6.3 | 18900000 | 190 | 3338 | 99473.6842 | Y | 11400000 | 634220 | 29.8004 | 1.4742 | -1 | 0
217-983R | 2 | 78 | 7 | 13132 | 7 | 21000000 | 78 | 13132 | 269230.7692 | Y | 4680000 | 1024296 | 20.5019 | 1.3118 | -0.75 | 0
220-288R | 1 | 261 | 2.04 | 20222 | 2.04 | 6120000 | 261 | 20222 | 23448.2759 |  | 6120000 | 5277942 | 1.1595 | 0.064287 | -0.5 | 1
220-298R | 3 | 132 | 10.72 | 20222 | 10.72 | 32160000 | 132 | 20222 | 243636.3636 | Y | 7920000 | 2669304 | 12.0481 | 1.0809 | -0.25 | 3
221-37AE | 1 | 915 | 5 | 23206 | 5 | 15000000 | 915 | 23206 | 16393.4426 |  | 15000000 | 21233490 | 0.70643 | -0.15093 | 0 | 3
222-1364R | 1 | 438 | 3.8 | 37264 | 3.8 | 11400000 | 438 | 37264 | 26027.3973 |  | 11400000 | 16321632 | 0.69846 | -0.15586 | 0.25 | 3
222-1401R | 1 | 260 | 1.73 | 37264 | 1.73 | 5190000 | 260 | 37264 | 19961.5385 |  | 5190000 | 9688640 | 0.53568 | -0.2711 | 0.5 | 0
222-1503, 222-2013R | 1 | 287 | 3.18 | 37264 | 3.18 | 9540000 | 287 | 37264 | 33240.4181 |  | 9540000 | 10694768 | 0.89202 | -0.049623 | 0.75 | 0
222-2013R | 1 | 245 | 4.18 | 37264 | 4.18 | 12540000 | 245 | 37264 | 51183.6735 |  | 12540000 | 9129680 | 1.3735 | 0.13784 | 1 | 2
441-23R | 1 | 75 | 6.12 | 23270 | 6.12 | 18360000 | 75 | 23270 | 244800 | Y | 4500000 | 1745250 | 10.52 | 1.022 | 1.25 | 2
442-729 | 1 | 1137 | 6.2 | 13500 | 6.2 | 18600000 | 1137 | 13500 | 16358.8391 |  | 18600000 | 15349500 | 1.2118 | 0.083419 | 1.5 | 0
445-1311R | 1 | 179 | 4.12 | 28176 | 4.12 | 12360000 | 179 | 28176 | 69050.2793 | Y | 10740000 | 5043504 | 2.4507 | 0.38929
Grand Total | 17 | 1137 | 60.89 | 37264 | 60.89 | 182670000 | 4410 | 37264 | 41421.7687 |  | 119130000 | 99523220 | 1.8355 | 0.26374
34.78%

## Sheet2
b) Program | SUG
Row Labels | Count of d) Circuit-Segment ID | Max of Total Customers | Sum of i) Length of SUG conductor to be installed in 2025 | Max of Minutes of PSPS Outage by Circuit | Length (mi) | Cost | Customers | Circuit Minutes | Cost/Customer | Off Grid $60k | OG Costs | Customer minutes | Cost/customer minute
210-172R | 1 | 213 | 0.5 | 3338 | 0.5 | 1500000 | 213 | 3338 | 7042.2535 |  | 1500000 | 710994 | 2.1097
210-9R | 2 | 190 | 6.3 | 3338 | 6.3 | 18900000 | 190 | 3338 | 99473.6842 | Y | 11400000 | 634220 | 29.8004
217-983R | 2 | 78 | 7 | 13132 | 7 | 21000000 | 78 | 13132 | 269230.7692 | Y | 4680000 | 1024296 | 20.5019
220-288R | 1 | 261 | 2.04 | 20222 | 2.04 | 6120000 | 261 | 20222 | 23448.2759 |  | 6120000 | 5277942 | 1.1595
220-298R | 3 | 132 | 10.72 | 20222 | 10.72 | 32160000 | 132 | 20222 | 243636.3636 | Y | 7920000 | 2669304 | 12.0481
221-37AE | 1 | 915 | 5 | 23206 | 5 | 15000000 | 915 | 23206 | 16393.4426 |  | 15000000 | 21233490 | 0.70643
222-1364R | 1 | 438 | 3.8 | 37264 | 3.8 | 11400000 | 438 | 37264 | 26027.3973 |  | 11400000 | 16321632 | 0.69846
222-1401R | 1 | 260 | 1.73 | 37264 | 1.73 | 5190000 | 260 | 37264 | 19961.5385 |  | 5190000 | 9688640 | 0.53568
222-1503, 222-2013R | 1 | 287 | 3.18 | 37264 | 3.18 | 9540000 | 287 | 37264 | 33240.4181 |  | 9540000 | 10694768 | 0.89202
222-2013R | 1 | 245 | 4.18 | 37264 | 4.18 | 12540000 | 245 | 37264 | 51183.6735 |  | 12540000 | 9129680 | 1.3735
441-23R | 1 | 75 | 6.12 | 23270 | 6.12 | 18360000 | 75 | 23270 | 244800 | Y | 4500000 | 1745250 | 10.52
442-729 | 1 | 1137 | 6.2 | 13500 | 6.2 | 18600000 | 1137 | 13500 | 16358.8391 |  | 18600000 | 15349500 | 1.2118
445-1311R | 1 | 179 | 4.12 | 28176 | 4.12 | 12360000 | 179 | 28176 | 69050.2793 | Y | 10740000 | 5043504 | 2.4507
Grand Total | 17 | 1137 | 60.89 | 37264 | 60.89 | 182670000 | 4410 | 37264 | 41421.7687 |  | 119130000 | 99523220 | 1.8355