## MGRA 004 Q010
PG&E's 2025-2028 Undergrounding Workplan
Prepared in response to data request GRC_MGRA_004, Question 010
Data as of 12/10/2025
[8 empty] | MGRA 004 Q010 Subpart | a | b | c | d
Circuit Segment | Circuit ID | Circuit Name | County | HFTD | Forecasted Year Complete | 2025-2028 Forecasted UG Miles | Estimated UG Unit Cost ($M/mile) | 2025-2028 Forecasted UG Cost ($M) | Total Wildfire Risk Points WDRM v4 | Percentile Ranking of Risk WDRM v4 | Benefit-Cost Ratio | Total Wildfire Risk Points WDRM v3 (for available Circuit Segments) | Percentile Rank of Risk WDRM v3 (for available Circuit Segments)
TIGER CREEK 0201CB | 161380201 | TIGER CREEK 0201 | AMADOR | Tier 2 & 3 | 2027 | 4.3384 | $1.5 - $6.1 | $6.6 - $26.3 | 0.46881 | 0.04% | 44.039 | 0.22518 | 0.07162%
BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | PLUMAS | Tier 2 & 3 | 2026 | 12.8222 | $1.5 - $6.1 | $19.4 - $77.7 | 0.019203 | 0.1% | 12.406 | 13.4627 | 0.4029%
APPLE HILL 2102CB | 153662102 | APPLE HILL 2102 | EL DORADO | Tier 2 & 3 | 2028 | 5 | $1.5 - $6.1 | $7.6 - $30.3 | 0.031693 | 0.13% | -158.21 | 0.13518 | 0.01791%
FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | SHASTA | Tier 2 | 2028 | 0.56 | $1.5 - $6.1 | $0.8 - $3.4 | 1.0497 | 0.24% | 6.943 | 0.61899 | 2.426%
DOBBINS 1101CB | 157341101 | DOBBINS 1101 | YUBA | Tier 2 | 2027 | 0.65 | $1.5 - $6.1 | $1 - $3.9 | 0.21261 | 0.26% | 8.587 | 0.090924 | 3.08%
CLAYTON 221296224 | 12022212 | CLAYTON 2212 | CONTRA COSTA | Tier 3 | 2026 | 0.78996 | $1.5 - $6.1 | $1.2 - $4.8 | 2.2782 | 0.27% | 7.324 | 4.7056 | 0.1343%
WEST POINT 1101CB | 163201101 | WEST POINT 1101 | AMADOR | Tier 3 | 2028 | 6.2722 | $1.5 - $6.1 | $9.5 - $38 | 1.3938 | 0.28% | 6.726 | 1.1303 | 1.952%
FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | SHASTA | Tier 2 | 2028 | 1.4002 | $1.5 - $6.1 | $2.1 - $8.5 | 1.9641 | 0.31% | 4.758 | 1.454 | 2.346%
CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | NAPA | Tier 3 | 2028 | 2.85 | $1.5 - $6.1 | $4.3 - $17.3 | 0.80807 | 0.32% | 8.387 | 0.41642 | 3.483%
MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | EL DORADO | Tier 2 | 2025 | 0.5108 | $1.5 - $6.1 | $0.8 - $3.1 | 0.014553 | 0.33% | 8.039 | 0.026347 | 0.949%
DRUM 1101CB | 152321101 | DRUM 1101 | PLACER | Tier 3 | 2026 | 0.27992 | $1.5 - $6.1 | $0.4 - $1.7 | 0.55208 | 0.34% | 7.479 | 0.69692 | 0.9221%
WISHON 1101CB | 251511101 | WISHON 1101 | MADERA | Tier 2 & 3 | 2028 | 0.038068 | $1.5 - $6.1 | $0.1 - $0.2 | 0.0085528 | 0.37% | 4.135 | 1.806 | 1.853%
ORO FINO 11022236 | 103031102 | ORO FINO 1102 | BUTTE | Tier 3 | 2028 | 0.65 | $1.5 - $6.1 | $1 - $3.9 | 0.62693 | 0.38% | 7.152 | 0.72907 | 1.155%
MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | LAKE | Tier 2 & 3 | 2028 | 16.01 | $1.5 - $6.1 | $24.3 - $97 | 4.1801 | 0.42% | 8.826 | 4.6566 | 1.656%
CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | SONOMA | Tier 3 | 2027 | 1.32 | $1.5 - $6.1 | $2 - $8 | 5.0593 | 0.44% | 6.497 | 3.26 | 3.348%
GUSTINE 1102999258 | 163111102 | GUSTINE 1102 | MERCED | HFRA | 2028 | 0.28542 | $1.5 - $6.1 | $0.4 - $1.7 | 1.6336 | 0.44% | 5.475 | 0.50125 | 6.723%
ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | AMADOR | Tier 2 | 2025 | 5.465 | $1.5 - $6.1 | $8.3 - $33.1 | 1.3015 | 0.45% | 6.188 | 1.9047 | 1.056%
PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | YUBA | Tier 3 | 2027 | 7.52 | $1.5 - $6.1 | $11.4 - $45.6 | 1.3121 | 0.48% | 5.831 | 2.4874 | 0.4655%
CLAYTON 2212681608 | 12022212 | CLAYTON 2212 | CONTRA COSTA | Tier 2 & 3 | 2026 | 0.043939 | $1.5 - $6.1 | $0.1 - $0.3 | 5.9511 | 0.49% | 6.968 | 8.669 | 1.03%
ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | SIERRA | Tier 3 | 2026 | 12.2037 | $1.5 - $6.1 | $18.5 - $74 | 3.8419 | 0.51% | 5.625 | 8.3828 | 0.3671%
ALTO 1124432 | 42031124 | ALTO 1124 | MARIN | Tier 3 | 2028 | 10.3 | $1.5 - $6.1 | $15.6 - $62.4 | 1.5974 | 0.52% | 11.572 | 0.50513 | 6.088%
PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | SHASTA | Tier 2 | 2028 | 13.3057 | $1.5 - $6.1 | $20.2 - $80.6 | 2.3896 | 0.57% | 5.385 | 1.6721 | 3.527%
PIT NO 5 1101CB | 103731101 | PIT NO 5 1101 | SHASTA | Tier 2 | 2026 | 0.67405 | $1.5 - $6.1 | $1 - $4.1 | 0.024785 | 0.6% | 5.884 | 0.25621 | 0.9311%
MIWUK 170236888 | 163661702 | MIWUK 1702 | TUOLUMNE | Tier 3 | 2027 | 0.42992 | $1.5 - $6.1 | $0.7 - $2.6 | 0.10676 | 0.63% | 4.106 | 0.19954 | 0.4476%
SILVERADO 2104646776 | 43432104 | SILVERADO 2104 | NAPA | Tier 3 | 2025 | 1.158 | $1.5 - $6.1 | $1.8 - $7 | 0.6106 | 0.66% | 5.565 | 2.4842 | 0.1253%
INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | MARIPOSA | Tier 2 | 2026 | 3.0773 | $1.5 - $6.1 | $4.7 - $18.6 | 1.7438 | 0.68% | 3.744 | 11.9266 | 0.08953%
MONTE RIO 1113320 | 42811113 | MONTE RIO 1113 | SONOMA | Tier 3 | 2028 | 7.77 | $1.5 - $6.1 | $11.8 - $47.1 | 0.68092 | 0.69% | 5.532 | 0.070229 | 12.94%
STELLING 11109265 | 83481110 | STELLING 1110 | SANTA CLARA | Tier 2 | 2028 | 6.84 | $1.5 - $6.1 | $10.4 - $41.5 | 0.9247 | 0.7% | 5.082 | 0.69174 | 3.796%
TEJON 11022455 | 252931102 | TEJON 1102 | KERN | Tier 2 | 2025 | 2.5017 | $1.5 - $6.1 | $3.8 - $15.2 | 1.0598 | 0.72% | 3.025 | 2.3484 | 0.6446%
EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | EL DORADO | Tier 3 | 2026 | 6.2423 | $1.5 - $6.1 | $9.5 - $37.8 | 1.1958 | 0.73% | -56.637 | 2.2121 | 0.7252%
HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | LAKE | Tier 2 & 3 | 2027 | 6.3352 | $1.5 - $6.1 | $9.6 - $38.4 | 2.9935 | 0.74% | 3.967 | 7.276 | 0.2596%
CALAVERAS CEMENT 1101544800 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS | Tier 2 | 2028 | 3.01 | $1.5 - $6.1 | $4.6 - $18.2 | 3.6669 | 0.77% | 3.525 | 3.7702 | 2.963%
ALTO 11243745 | 42031124 | ALTO 1124 | MARIN | Tier 3 | 2028 | 5.19 | $1.5 - $6.1 | $7.9 - $31.5 | 0.7089 | 0.78% | 5.804 | 0.27831 | 6.329%
PINE GROVE 110245292 | 167351102 | PINE GROVE 1102 | AMADOR | Tier 2 & 3 | 2027 | 12.5795 | $1.5 - $6.1 | $19.1 - $76.2 | 1.6767 | 0.79% | 4.537 | 2.1846 | 2.086%
SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | SAN LUIS OBISPO | Tier 3 | 2028 | 3.2 | $1.5 - $6.1 | $4.8 - $19.4 | 1.2968 | 0.82% | 4.255 | 0.56284 | 6.652%
BONNIE NOOK 1102542186 | 152301102 | BONNIE NOOK 1102 | PLACER | Tier 3 | 2028 | 5.7991 | $1.5 - $6.1 | $8.8 - $35.1 | 1.1607 | 0.84% | 3.297 | N/A | N/A
BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | PLUMAS | Tier 3 | 2028 | 0.12 | $1.5 - $6.1 | $0.2 - $0.7 | 0.33843 | 0.88% | 5.021 | 0.3893 | 3.617%
BIG BEND 1101CB | 103751101 | BIG BEND 1101 | BUTTE | Tier 3 | 2028 | 22.47 | $1.5 - $6.1 | $34 - $136.2 | 3.3204 | 0.9% | 6.918 | 4.707 | 2.184%
FORT ROSS 112170288 | 42851121 | FORT ROSS 1121 | SONOMA | Tier 2 & 3 | 2028 | 32.37 | $1.5 - $6.1 | $49 - $196.2 | 3.3854 | 0.93% | 4.057 | 0.73399 | 10.98%
ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | SIERRA | Tier 3 | 2027 | 4.4055 | $1.5 - $6.1 | $6.7 - $26.7 | 0.56789 | 0.94% | 3.497 | 1.2 | 1.146%
CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | CALAVERAS | Tier 2 | 2027 | 5.54 | $1.5 - $6.1 | $8.4 - $33.6 | 2.0624 | 0.95% | 3.144 | 3.6329 | 1.773%
PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | SHASTA | Tier 2 | 2025 | 5.7434 | $1.5 - $6.1 | $8.7 - $34.8 | 0.61588 | 0.97% | 6.662 | 0.79754 | 2.919%
ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | SIERRA | Tier 3 | 2028 | 3.752 | $1.5 - $6.1 | $5.7 - $22.7 | 1.5268 | 0.98% | 3.071 | 2.4553 | 2.274%
MIWUK 17021808 | 163661702 | MIWUK 1702 | TUOLUMNE | Tier 3 | 2028 | 1.74 | $1.5 - $6.1 | $2.6 - $10.5 | 0.23429 | 0.98% | 2.761 | 0.40387 | 1.934%
ELECTRA 11017104 | 162161101 | ELECTRA 1101 | AMADOR | Tier 2 | 2025 | 9.3498 | $1.5 - $6.1 | $14.2 - $56.7 | 1.6266 | 0.99% | 5.889 | 4.3703 | 0.5551%
CORNING 110185152 | 103331101 | CORNING 1101 | TEHAMA | Tier 2 | 2027 | 2.24 | $1.5 - $6.1 | $3.4 - $13.6 | 3.0998 | 1% | 4.243 | 5.6966 | 1.737%
STELLING 1110568350 | 83481110 | STELLING 1110 | SANTA CLARA | Tier 2 | 2028 | 6.7399 | $1.5 - $6.1 | $10.2 - $40.8 | 1.5472 | 1.01% | 4.474 | 0.78785 | 6.482%
SILVERADO 2104324994 | 43432104 | SILVERADO 2104 | NAPA | Tier 3 | 2027 | 0.26 | $1.5 - $6.1 | $0.4 - $1.6 | 0.086596 | 1.04% | 12.974 | 0.032616 | 7.816%
NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | BUTTE | Tier 3 | 2026 | 12.8316 | $1.5 - $6.1 | $19.4 - $77.8 | 1.3942 | 1.07% | 3.53 | 4.9411 | 0.3312%
PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | EL DORADO | Tier 2 & 3 | 2028 | 11.8002 | $1.5 - $6.1 | $17.9 - $71.5 | 0.82378 | 1.09% | 88.697 | 1.2865 | 2.059%
CLAYTON 2212614950 | 12022212 | CLAYTON 2212 | CONTRA COSTA | Tier 2 & 3 | 2025 | 0.59015 | $1.5 - $6.1 | $0.9 - $3.6 | 0.17872 | 1.1% | 9.354 | 0.44617 | 0.8953%
PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | SIERRA | Tier 3 | 2028 | 13.1241 | $1.5 - $6.1 | $19.9 - $79.5 | 1.1889 | 1.12% | 3.125 | 2.6533 | 1.45%
SUNOL 1101298061 | 14241101 | SUNOL 1101 | ALAMEDA | Tier 3 | 2028 | 2.47 | $1.5 - $6.1 | $3.7 - $15 | 0.61136 | 1.14% | 3.65 | N/A | N/A
FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | PLACER | Tier 3 | 2025 | 3.4508 | $1.5 - $6.1 | $5.2 - $20.9 | 1.4406 | 1.16% | 6.123 | 3.8647 | 1.021%
MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | EL DORADO | Tier 2 & 3 | 2028 | 28.09 | $1.5 - $6.1 | $42.6 - $170.2 | 2.4438 | 1.17% | 4.979 | 2.8022 | 3.402%
CALISTOGA 1101730666 | 42711101 | CALISTOGA 1101 | SONOMA | Tier 2 & 3 | 2028 | 2.29 | $1.5 - $6.1 | $3.5 - $13.9 | 0.26722 | 1.18% | 3.027 | N/A | N/A
PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | SHASTA | Tier 2 | 2028 | 2.65 | $1.5 - $6.1 | $4 - $16.1 | 0.30943 | 1.2% | 4.624 | 0.33168 | 3.76%
BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | PLACER | Tier 3 | 2026 | 19.1788 | $1.5 - $6.1 | $29.1 - $116.2 | 1.7292 | 1.22% | 6.138 | 8.3015 | 0.1791%
MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | Mariposa | Tier 2 & 3 | 2028 | 6.0719 | $1.5 - $6.1 | $9.2 - $36.8 | 2.3126 | 1.23% | 2.137 | 3.9784 | 2.167%
ALTO 11221260 | 42031122 | ALTO 1122 | Marin | Tier 2 & 3 | 2028 | 3.5513 | $1.5 - $6.1 | $5.4 - $21.5 | 0.35613 | 1.25% | 9.733 | 0.058051 | 12.25%
WEST POINT 110236676 | 163201102 | WEST POINT 1102 | Calaveras | Tier 2 & 3 | 2028 | 15.6 | $1.5 - $6.1 | $23.6 - $94.5 | 1.9741 | 1.25% | 2.687 | 4.652 | 1.379%
APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | EL DORADO | Tier 3 | 2028 | 31.84 | $1.5 - $6.1 | $48.2 - $193 | 3.0103 | 1.28% | 3.463 | 6.1639 | 1.764%
KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | Lake | Tier 2 | 2028 | 3.0125 | $1.5 - $6.1 | $4.6 - $18.3 | 0.3149 | 1.29% | 2.926 | 0.40181 | 2.972%
PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | Shasta | Tier 2 | 2028 | 1.425 | $1.5 - $6.1 | $2.2 - $8.6 | 0.53575 | 1.3% | 3.405 | 0.59511 | 3.599%
SARATOGA 1107667000 | 83371107 | SARATOGA 1107 | Santa Clara | Tier 2 & 3 | 2028 | 9.1661 | $1.5 - $6.1 | $13.9 - $55.5 | 0.85548 | 1.31% | 4.086 | N/A | N/A
SILVERADO 210478268 | 43432104 | SILVERADO 2104 | NAPA | Tier 3 | 2027 | 16.6597 | $1.5 - $6.1 | $25.2 - $101 | 1.3136 | 1.32% | 6.439 | 3.9906 | 0.9042%
ELECTRA 1101CB | 162161101 | ELECTRA 1101 | Amador | Tier 2 | 2028 | 7.275 | $1.5 - $6.1 | $11 - $44.1 | 2.6802 | 1.34% | 3.489 | 4.6905 | 2.247%
CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | Tier 2 & 3 | 2028 | 21.5125 | $1.5 - $6.1 | $32.6 - $130.4 | 1.9539 | 1.37% | 2.762 | 3.4528 | 2.328%
PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | El Dorado | Tier 2 & 3 | 2028 | 23.1656 | $1.5 - $6.1 | $35.1 - $140.4 | 2.8205 | 1.38% | 4.478 | 5.499 | 2.113%
DUNLAP 1103CB | 254061103 | DUNLAP 1103 | Fresno | Tier 2 | 2028 | 1.7281 | $1.5 - $6.1 | $2.6 - $10.5 | 0.62851 | 1.38% | 2.229 | 0.45572 | 5.309%
SILVERADO 2104632 | 43432104 | SILVERADO 2104 | NAPA | Tier 3 | 2026 | 26.2107 | $1.5 - $6.1 | $39.7 - $158.8 | 2.0683 | 1.39% | 5.834 | 7.1206 | 0.5282%
SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | Santa Barbara | Tier 2 & 3 | 2028 | 10.3163 | $1.5 - $6.1 | $15.6 - $62.5 | 1.9501 | 1.4% | 7.31 | 0.69781 | 9.248%
SHADY GLEN 1101941844 | 152431101 | SHADY GLEN 1101 | Placer | Tier 2 | 2028 | 15.2616 | $1.5 - $6.1 | $23.1 - $92.5 | 1.878 | 1.41% | 3.144 | 0.020708 | 12.71%
MOLINO 1102318 | 42571102 | MOLINO 1102 | Sonoma | Tier 3 | 2028 | 24.3291 | $1.5 - $6.1 | $36.9 - $147.4 | 2.8686 | 1.43% | 3.18 | 0.36374 | 15.28%
PINE GROVE 1101CB | 167351101 | PINE GROVE 1101 | AMADOR | Tier 2 | 2027 | 3.6889 | $1.5 - $6.1 | $5.6 - $22.4 | 0.4682 | 1.44% | 5.043 | 3.4028 | 0.05372%
STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | CALAVERAS | Tier 2 | 2028 | 2.6121 | $1.5 - $6.1 | $4 - $15.8 | 3.9919 | 1.45% | 3.029 | 12.2141 | 0.8505%
STILLWATER 11021466 | 103561102 | STILLWATER 1102 | Shasta | Tier 2 | 2028 | 19.0406 | $1.5 - $6.1 | $28.8 - $115.4 | 2.2092 | 1.46% | 2.801 | 4.5093 | 1.97%
LAURELES 111110141 | 182371111 | LAURELES 1111 | Monterey | Tier 3 | 2028 | 3.5838 | $1.5 - $6.1 | $5.4 - $21.7 | 0.31172 | 1.48% | 2.534 | 0.18492 | 6.992%
WEST POINT 11021305 | 163201102 | WEST POINT 1102 | Calaveras | Tier 3 | 2028 | 4.3551 | $1.5 - $6.1 | $6.6 - $26.4 | 1.2266 | 1.51% | 2.132 | 2.6234 | 1.844%
PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | EL DORADO | Tier 3 | 2027 | 32.3883 | $1.5 - $6.1 | $49.1 - $196.3 | 2.1993 | 1.56% | 2.215 | 8.4164 | 0.5192%
TEJON 11023751 | 252931102 | TEJON 1102 | KERN | Tier 2 | 2025 | 8.1602 | $1.5 - $6.1 | $12.4 - $49.5 | 0.9706 | 1.6% | 4.463 | 1.351 | 3.295%
SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | PLACER | Tier 2 | 2026 | 3.7555 | $1.5 - $6.1 | $5.7 - $22.8 | 0.75016 | 1.72% | 3.151 | 2.4427 | 1.074%
MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | LAKE | Tier 3 | 2027 | 11.6727 | $1.5 - $6.1 | $17.7 - $70.7 | 2.6568 | 1.76% | 5.163 | 9.4271 | 0.9132%
STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | CALAVERAS | Tier 3 | 2026 | 7.6784 | $1.5 - $6.1 | $11.6 - $46.5 | 0.80371 | 1.77% | 3.684 | 2.7653 | 0.5372%
REDBUD 1101323962 | 43191101 | REDBUD 1101 | LAKE | Tier 2 & 3 | 2026 | 6.3106 | $1.5 - $6.1 | $9.6 - $38.2 | 2.3419 | 1.78% | 5.68 | 8.9972 | 1.137%
STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | CALAVERAS | Tier 3 | 2028 | 25.5032 | $1.5 - $6.1 | $38.6 - $154.6 | 1.8319 | 1.83% | 2.321 | 7.1619 | 0.5909%
PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | EL DORADO | Tier 2 & 3 | 2027 | 30.4945 | $1.5 - $6.1 | $46.2 - $184.8 | 4.0009 | 1.87% | 3.347 | 16.1566 | 0.6088%
KESWICK 110148480 | 103451101 | KESWICK 1101 | SHASTA | Tier 3 | 2026 | 0.20833 | $1.5 - $6.1 | $0.3 - $1.3 | 0.99113 | 1.88% | 2.159 | 2.8989 | 1.065%
WEST POINT 110112256 | 163201101 | WEST POINT 1101 | AMADOR | Tier 3 | 2028 | 13.3073 | $1.5 - $6.1 | $20.2 - $80.6 | 0.61224 | 1.91% | 3.027 | 0.88667 | 3.151%
CURTIS 17039240 | 163351701 | CURTIS 1703 | TUOLUMNE | Tier 2 & 3 | 2028 | 17.0117 | $1.5 - $6.1 | $25.8 - $103.1 | 1.0147 | 1.95% | 2.757 | 4.0927 | 0.5998%
ANTLER 11011384 | 103271101 | ANTLER 1101 | SHASTA | Tier 2 | 2025 | 15.1652 | $1.5 - $6.1 | $23 - $91.9 | 0.38658 | 1.99% | 3.903 | 5.772 | 0.09848%
MIDDLETOWN 1101171414 | 43141101 | MIDDLETOWN 1101 | LAKE | Tier 3 | 2026 | 2.5169 | $1.5 - $6.1 | $3.8 - $15.3 | 0.32251 | 2.01% | 2.664 | 1.6171 | 0.3402%
EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | EL DORADO | Tier 3 | 2028 | 6.77 | $1.5 - $6.1 | $10.3 - $41 | 0.5062 | 2.03% | 10.641 | 0.77456 | 2.489%
TEJON 1102732836 | 252931102 | TEJON 1102 | KERN | Tier 2 | 2028 | 14.537 | $1.5 - $6.1 | $22 - $88.1 | 1.4125 | 2.08% | 3.504 | 3.5396 | 1.961%
ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | SIERRA | Tier 2 & 3 | 2028 | 6.4801 | $1.5 - $6.1 | $9.8 - $39.3 | 1.6693 | 2.09% | 2.845 | 1.4142 | 5.837%
SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | PLACER | Tier 2 | 2026 | 11.057 | $1.5 - $6.1 | $16.8 - $67 | 0.6888 | 2.1% | 2.206 | 4.5113 | 0.6356%
CALISTOGA 1102131531 | 42711102 | CALISTOGA 1102 | NAPA | Tier 3 | 2025 | 1.8312 | $1.5 - $6.1 | $2.8 - $11.1 | 0.43305 | 2.11% | 2.711 | 2.4772 | 0.2149%
FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | PLACER | Tier 3 | 2028 | 33.3231 | $1.5 - $6.1 | $50.5 - $201.9 | 1.9812 | 2.12% | 6.32 | 5.7413 | 1.603%
WEST POINT 110277204 | 163201102 | WEST POINT 1102 | CALAVERAS | Tier 2 & 3 | 2028 | 3.46 | $1.5 - $6.1 | $5.2 - $21 | 0.65624 | 2.2% | 1.638 | 2.4292 | 0.9848%
BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | PLACER | Tier 3 | 2028 | 42.593 | $1.5 - $6.1 | $64.5 - $258.1 | 2.2557 | 2.29% | 4.089 | 8.4066 | 1.719%
MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | EL DORADO | Tier 2 | 2026 | 0.14375 | $1.5 - $6.1 | $0.2 - $0.9 | 0.62517 | 2.3% | 2.767 | 2.5439 | 0.6267%
STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | CALAVERAS | Tier 3 | 2026 | 9.6691 | $1.5 - $6.1 | $14.6 - $58.6 | 0.57802 | 2.33% | 3.367 | 1.9589 | 0.8774%
ORO FINO 1102CB | 103031102 | ORO FINO 1102 | BUTTE | Tier 3 | 2026 | 3.26 | $1.5 - $6.1 | $4.9 - $19.8 | 0.18183 | 2.34% | -13.387 | 1.3156 | 0.1522%
MIDDLETOWN 11011314 | 43141101 | MIDDLETOWN 1101 | LAKE | Tier 2 & 3 | 2027 | 1.05 | $1.5 - $6.1 | $1.6 - $6.4 | 0.074754 | 2.41% | 2.14 | 0.41204 | 0.5013%
VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | SOLANO | Tier 2 | 2025 | 0.13428 | $1.5 - $6.1 | $0.2 - $0.8 | 0.96252 | 2.47% | 8.465 | 1.2513 | 6.876%
SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | BUTTE | Tier 3 | 2028 | 25.1142 | $1.5 - $6.1 | $38 - $152.2 | 1.6978 | 2.49% | 3.041 | 8.4684 | 0.5103%
ORO FINO 110276008 | 103031102 | ORO FINO 1102 | BUTTE | Tier 3 | 2026 | 17.8316 | $1.5 - $6.1 | $27 - $108.1 | 1.2853 | 2.55% | 2.273 | 5.8121 | 0.5461%
OAKHURST 110310140 | 254421103 | OAKHURST 1103 | MADERA | Tier 3 | 2027 | 6.3411 | $1.5 - $6.1 | $9.6 - $38.4 | 1.3038 | 2.62% | 1.736 | 9.0145 | 0.197%
WEST POINT 11021341 | 163201102 | WEST POINT 1102 | CALAVERAS | Tier 3 | 2025 | 10.1744 | $1.5 - $6.1 | $15.4 - $61.7 | 0.76794 | 2.63% | 1.785 | 3.3233 | 0.7162%
PUEBLO 2103678 | 43292103 | PUEBLO 2103 | NAPA | Tier 2 & 3 | 2028 | 65.9916 | $1.5 - $6.1 | $100 - $399.9 | 2.7053 | 2.67% | 2.953 | 6.6617 | 2.283%
MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | MARIPOSA | Tier 2 & 3 | 2027 | 2.4483 | $1.5 - $6.1 | $3.7 - $14.8 | 1.5219 | 2.8% | 2.054 | 6.2842 | 1.128%
KESWICK 11019712 | 103451101 | KESWICK 1101 | SHASTA | Tier 3 | 2026 | 6.0155 | $1.5 - $6.1 | $9.1 - $36.5 | 1.3849 | 2.8% | 1.202 | 8.0408 | 0.385%
WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | SHASTA | Tier 2 | 2026 | 4.66 | $1.5 - $6.1 | $7.1 - $28.2 | 0.36345 | 2.94% | 1.883 | 1.7355 | 0.9758%
APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | EL DORADO | Tier 2 | 2025 | 7.1489 | $1.5 - $6.1 | $10.8 - $43.3 | 0.86935 | 2.95% | 1.69 | 5.7862 | 0.2865%
PEORIA 170190090 | 163781701 | PEORIA 1701 | TUOLUMNE | Tier 2 | 2026 | 1.8939 | $1.5 - $6.1 | $2.9 - $11.5 | 2.1289 | 3.03% | 1.819 | 9.5205 | 1.092%
OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | SHASTA | Tier 2 | 2026 | 6.7585 | $1.5 - $6.1 | $10.2 - $41 | 0.92513 | 3.05% | 1.348 | 5.2 | 0.573%
MIDDLETOWN 1101433160 | 43141101 | MIDDLETOWN 1101 | LAKE | Tier 2 & 3 | 2026 | 1.35 | $1.5 - $6.1 | $2 - $8.2 | 0.10837 | 3.09% | 3.237 | 0.60598 | 0.8863%
WEST POINT 11014706 | 163201101 | WEST POINT 1101 | AMADOR | Tier 3 | 2027 | 13.5595 | $1.5 - $6.1 | $20.5 - $82.2 | 0.80729 | 3.21% | 3.397 | 3.7702 | 0.9579%
DOBBINS 110169722 | 157341101 | DOBBINS 1101 | YUBA | Tier 2 | 2027 | 0.67 | $1.5 - $6.1 | $1 - $4.1 | 0.43753 | 3.35% | 2.178 | 1.1933 | 2.525%
APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | EL DORADO | Tier 2 | 2025 | 1.0748 | $1.5 - $6.1 | $1.6 - $6.5 | 0.36551 | 3.41% | 1.313 | 1.9545 | 0.4924%
BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | BUTTE | Tier 3 | 2026 | 0.7 | $1.5 - $6.1 | $1.1 - $4.2 | 0.34163 | 3.52% | 1.541 | 1.6192 | 0.9669%
APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | EL DORADO | Tier 2 | 2025 | 5.2638 | $1.5 - $6.1 | $8 - $31.9 | 0.26092 | 3.53% | 10.579 | 1.8567 | 0.2686%
APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | EL DORADO | Tier 2 & 3 | 2025 | 31.2998 | $1.5 - $6.1 | $47.4 - $189.7 | 1.4199 | 3.68% | 2.113 | 8.7516 | 0.564%
SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | PLACER | Tier 2 & 3 | 2026 | 10.1366 | $1.5 - $6.1 | $15.4 - $61.4 | 0.68912 | 3.73% | 1.654 | 4.0016 | 0.7968%
BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | MARIPOSA | Tier 2 | 2026 | 2.14 | $1.5 - $6.1 | $3.2 - $13 | 0.28009 | 3.75% | 1.328 | 1.6917 | 0.6804%
SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | PLACER | Tier 2 & 3 | 2027 | 28.2117 | $1.5 - $6.1 | $42.7 - $171 | 1.1382 | 3.95% | 4.124 | 7.0586 | 0.8326%
COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | NEVADA | Tier 2 | 2026 | 2.9725 | $1.5 - $6.1 | $4.5 - $18 | 0.41688 | 3.95% | 1.256 | 3.1353 | 0.6714%
AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | FRESNO | Tier 2 | 2026 | 0.9786 | $1.5 - $6.1 | $1.5 - $5.9 | 2.619 | 3.99% | 1.175 | 3.8105 | 5.094%
ANTLER 1101CB | 103271101 | ANTLER 1101CB | SHASTA | Tier 2 | 2026 | 0.83258 | $1.5 - $6.1 | $1.3 - $5 | 0.089185 | 4.09% | 1.866 | 0.47686 | 0.8415%
DOBBINS 11015202 | 157341101 | DOBBINS 1101 | YUBA | Tier 2 | 2028 | 0.17843 | $1.5 - $6.1 | $0.3 - $1.1 | 0.96039 | 4.14% | 1.429 | 0.9918 | 7.466%
PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | SIERRA | Tier 3 | 2027 | 21.9781 | $1.5 - $6.1 | $33.3 - $133.2 | 0.0406 | 4.28% | 4.021 | 6.3025 | 1.038%
CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | NAPA | Tier 3 | 2025 | 3.0061 | $1.5 - $6.1 | $4.6 - $18.2 | 0.50349 | 4.36% | 4.114 | 3.1179 | 0.94%
GIRVAN 11029012 | 103401102 | GIRVAN 1102 | SHASTA | Tier 2 & 3 | 2026 | 0.33996 | $1.5 - $6.1 | $0.5 - $2.1 | 0.82127 | 4.42% | 0.882 | 5.5179 | 0.6535%
HIGHLANDS 1103726580 | 43361103 | HIGHLANDS 1103 | LAKE | Tier 2 | 2026 | 0.73011 | $1.5 - $6.1 | $1.1 - $4.4 | 0.43596 | 4.62% | 1.45 | 2.5116 | 1.289%
ALTO 1124430 | 42031124 | ALTO 1124 | MARIN | Tier 3 | 2027 | 0.83 | $1.5 - $6.1 | $1.3 - $5 | 0.36069 | 4.62% | 5.779 | 0.51502 | 5.551%
PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | EL DORADO | Tier 2 | 2025 | 5.465 | $1.5 - $6.1 | $8.3 - $33.1 | 0.64772 | 4.81% | 1.615 | 3.6691 | 1.325%
MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | EL DORADO | Tier 2 | 2025 | 1.1206 | $1.5 - $6.1 | $1.7 - $6.8 | 1.09 | 4.83% | 1.825 | 2.6799 | 3.59%
ANTLER 11011520 | 103271101 | ANTLER 1101 | SHASTA | Tier 2 | 2025 | 4.1712 | $1.5 - $6.1 | $6.3 - $25.3 | 0.16622 | 4.96% | 1.465 | 3.1742 | 0.8147%
APPLE HILL 2102836878 | 153662102 | APPLE HILL 2102 | EL DORADO | Tier 2 & 3 | 2028 | 67.702 | $1.5 - $6.1 | $102.6 - $410.3 | 1.9469 | 5.09% | 3.854 | 12.0608 | 1.182%
JAMESON 110265516 | 63801102 | JAMESON 1102 | SOLANO | Tier 2 | 2026 | 0.8108 | $1.5 - $6.1 | $1.2 - $4.9 | 0.49702 | 5.23% | 2.907 | 1.7973 | 2.802%
KESWICK 11011588 | 103451101 | KESWICK 1101 | SHASTA | Tier 2 & 3 | 2026 | 2.1638 | $1.5 - $6.1 | $3.3 - $13.1 | 0.37626 | 5.76% | 0.818 | 3.2678 | 0.7431%
VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | SOLANO | Tier 2 | 2025 | 0.16761 | $1.5 - $6.1 | $0.3 - $1 | 0.49394 | 5.97% | 8.58 | 1.9083 | 3.429%
WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | SAN MATEO | Tier 3 | 2025 | 0.71932 | $1.5 - $6.1 | $1.1 - $4.4 | 0.5439 | 6.31% | 1.99 | 0.53258 | 9.185%
MONTE RIO 111164758 | 42851111 | MONTE RIO 1111 | SONOMA | Tier 3 | 2027 | 0.76 | $1.5 - $6.1 | $1.2 - $4.6 | 0.41767 | 6.49% | 1.435 | 0.43278 | 9.266%
SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | BUTTE | Tier 2 & 3 | 2027 | 2.7835 | $1.5 - $6.1 | $4.2 - $16.9 | 0.83318 | 6.95% | 1.1 | 2.823 | 3.885%
MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | LAKE | Tier 2 | 2027 | 1.9561 | $1.5 - $6.1 | $3 - $11.9 | 0.19391 | 7.12% | 2.778 | 0.75852 | 3.509%
CALISTOGA 1101122350 | 42711101 | CALISTOGA 1101 | NAPA | Tier 2 & 3 | 2028 | 5.0621 | $1.5 - $6.1 | $7.7 - $30.7 | 0.073197 | 7.47% | 3.748 | 4.0369 | 1.2%
SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | NAPA | Tier 3 | 2026 | 4.16 | $1.5 - $6.1 | $6.3 - $25.2 | 0.56731 | 8% | 1.116 | 6.1774 | 0.7789%
MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | MARIPOSA | Tier 2 & 3 | 2027 | 3.1559 | $1.5 - $6.1 | $4.8 - $19.1 | 2.0029 | 8.19% | 0.766 | 6.1299 | 4.512%
FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | PLACER | Tier 2 & 3 | 2027 | 2.1695 | $1.5 - $6.1 | $3.3 - $13.1 | 0.35687 | 8.6% | 1.439 | 1.9522 | 2.883%
ANTLER 11011612 | 103271101 | ANTLER 1101 | SHASTA | Tier 2 & 3 | 2026 | 4.9222 | $1.5 - $6.1 | $7.5 - $29.8 | 0.23501 | 8.84% | 0.865 | 2.4998 | 1.28%
CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | SHASTA | Tier 2 | 2025 | 0.015152 | $1.5 - $6.1 | $0 - $0.1 | 0.79062 | 10.15% | 1.721 | 2.5079 | 5.228%
FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | PLACER | Tier 2 & 3 | 2026 | 29.664 | $1.5 - $6.1 | $44.9 - $179.8 | 0.25384 | 10.22% | 1.616 | 9.8393 | 0.8684%
MOLINO 110266006 | 42571102 | Molino 1102 | SONOMA | Tier 3 | 2025 | 1.1309 | $1.5 - $6.1 | $1.7 - $6.9 | 0.23792 | 10.48% | 1.01 | 0.13232 | 15.4%
ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | GLENN | Tier 2 | 2025 | 0.80076 | $1.5 - $6.1 | $1.2 - $4.9 | 0.71073 | 11.68% | 5.018 | 1.2027 | 9.346%
VACAVILLE 110847860 | 63601108 | VACAVILLE 1108 | SOLANO | Tier 2 | 2025 | 0.42216 | $1.5 - $6.1 | $0.6 - $2.6 | 0.078761 | 13.54% | -7.27 | 0.036061 | 17.22%
POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | MENDOCINO | Tier 2 | 2027 | 2.4494 | $1.5 - $6.1 | $3.7 - $14.8 | 0.81976 | 13.92% | 0.828 | 3.5307 | 5.13%
GANSNER 11012424 | 103021101 | GANSNER 1101 | PLUMAS | Tier 2 & 3 | 2025 | 0.22519 | $1.5 - $6.1 | $0.3 - $1.4 | 0.26837 | 14.78% | 0.515 | 1.1306 | 7.028%
CORNING 1102915324 | 103331102 | CORNING 1102 | TEHAMA | Tier 2 | 2025 | 0.093182 | $1.5 - $6.1 | $0.1 - $0.6 | 0.06073 | 15.22% | 1.726 | 0.010255 | 26%
SILVERADO 2104708 | 43432104 | SILVERADO 2104 | NAPA | Tier 3 | 2025 | 4.0038 | $1.5 - $6.1 | $6.1 - $24.3 | 0.083283 | 15.74% | 8.356 | 0.37431 | 5.542%
BIG BASIN 11025066 | 82841102 | BIG BASIN 1102 | SANTA CRUZ | Tier 3 | 2025 | 5.5604 | $1.5 - $6.1 | $8.4 - $33.7 | 0.099279 | 16.96% | 0.596 | 0.23797 | 11.76%
SILVERADO 2104515946 | 43432104 | SILVERADO 2104 | NAPA | Tier 3 | 2026 | 12.9577 | $1.5 - $6.1 | $19.6 - $78.5 | 0.069538 | 17.38% | 3.619 | 7.9091 | 0.2954%
HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | SAN MATEO | Tier 2 | 2028 | 0.85814 | $1.5 - $6.1 | $1.3 - $5.2 | 0.12324 | 17.41% | 1.713 | 0.082057 | 21.79%
REDBUD 1101708166 | 43191101 | REDBUD 1101 | LAKE | Tier 2 & 3 | 2025 | 1.811 | $1.5 - $6.1 | $2.7 - $11 | 0.16568 | 17.48% | 1.319 | 0.80868 | 6.079%
OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | SHASTA | Tier 2 | 2025 | 4.2691 | $1.5 - $6.1 | $6.5 - $25.9 | 0.75442 | 18.08% | 1.063 | 0.34216 | 21.53%
CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | PLUMAS | Tier 2 | 2025 | 2.3386 | $1.5 - $6.1 | $3.5 - $14.2 | 0.10148 | 18.14% | 1.138 | 0.34238 | 7.645%
AUBERRY 1101CB | 254151101 | AUBERRY 1101 | FRESNO | Tier 2 | 2025 | 0.016667 | $1.5 - $6.1 | $0 - $0.1 | 0.24408 | 19.83% | 2.593 | 0.16403 | 19.03%
CLARK ROAD 1102CB | 103091102 | CLARK ROAD 1102 | BUTTE | Tier 2 | 2026 | 0.89091 | $1.5 - $6.1 | $1.4 - $5.4 | 0.019792 | 20.09% | 2.615 | 0.0080788 | 22.3%
DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | EL DORADO | Tier 2 | 2026 | 1.3299 | $1.5 - $6.1 | $2 - $8.1 | 0.48599 | 21.09% | 0.289 | 1.3497 | 10.6%
PEORIA 170510580 | 163781705 | PEORIA 1705 | TUOLUMNE | Tier 2 | 2025 | 0.074811 | $1.5 - $6.1 | $0.1 - $0.5 | 0.111 | 25.43% | 0.722 | 0.14728 | 15.92%
BIG MEADOWS 21012260 | 102812101 | BIG MEADOWS 2101 | PLUMAS | HFRA Buffer Zone, Tier 2 | 2025 | 5.307 | $1.5 - $6.1 | $8 - $32.2 | 0.14456 | 27.56% | 0.479 | 0.13429 | 19.11%
BELL 11082202 | 152701108 | BELL 1108 | PLACER | Tier 2 | 2026 | 3.7981 | $1.5 - $6.1 | $5.8 - $23 | 0.16363 | 28.03% | 0.311 | 0.11159 | 24.04%
POINT MORETTI 110112122 | 82931101 | POINT MORETTI 1101 | SANTA CRUZ | Tier 2 | 2026 | 1.1119 | $1.5 - $6.1 | $1.7 - $6.7 | 0.062155 | 33.28% | 0.373 | 0.071659 | 19.84%
EL CERRITO G 1105BR160 | 12501105 | El Cerrito G 1105 | ALAMEDA | Tier 2 & 3 | 2026 | 1.7312 | $1.5 - $6.1 | $2.6 - $10.5 | 0.07528 | 35.46% | 3.076 | 0.050823 | 23.57%
BIG MEADOWS 21012476 | 102812101 | BIG MEADOWS 2101 | PLUMAS | Tier 2 | 2028 | 1.09 | $1.5 - $6.1 | $1.7 - $6.6 | 0.04813 | 43.68% | 0.719 | 0.15782 | 13.72%
CALISTOGA 1101894 | 42711101 | CALISTOGA 1101 | NAPA | HFRA | 2025 | 0.19697 | $1.5 - $6.1 | $0.3 - $1.2 | 0.012098 | 50.02% | -0.495 | 0.0022546 | 40.92%
DUNBAR 1101CB | 43071101 | DUNBAR 1101 | SONOMA | Tier 2 | 2025 | 0.43333 | $1.5 - $6.1 | $0.7 - $2.6 | 0.012643 | 50.82% | -3.051 | 0.0057226 | 27.03%
MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | LAKE | Tier 3 | 2027 | 1.4515 | $1.5 - $6.1 | $2.2 - $8.8 | N/A | N/A | N/A | 5.7643 | 0.1164%
MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | MARIPOSA | Tier 2 & 3 | 2026 | 2.6763 | $1.5 - $6.1 | $4.1 - $16.2 | N/A | N/A | N/A | N/A | N/A
DUNBAR 1103534 | 43071101 | DUNBAR 1101 | SONOMA | Tier 2 & 3 | 2026 | 1.6792 | $1.5 - $6.1 | $2.5 - $10.2 | N/A | N/A | N/A | N/A | N/A
CURTIS 170356972 | 163351701 | CURTIS 1703 | TUOLUMNE | Tier 2 | 2026 | 0.24508 | $1.5 - $6.1 | $0.4 - $1.5 | N/A | N/A | N/A | 4.0241 | 0.3044%