## MGRA 006 Q003
Prepared in response to data request GRC_MGRA_006, Question 003
Data as of 1/28/2026
[5 empty] | Q3 Subparts > | a | b |  | c
Circuit Segment | Circuit ID | Circuit Name | County | Total Wildfire Risk Points (WDRM v3) | Percentile Rank of Risk (WDRM v3) | Planned Hardening | Total Segment Length (Primary Conductor Overhead Miles) | Planned Hardened Circuit Length (Primary Conductor Overhead Miles) | Forecasted Year of Completion
PINE GROVE 1101CB | 163751101 | PINE GROVE 1101 | Amador | 6 | 0.05372% | UG | 4.2753 |  | 2024
MONTICELLO 1101630 | 43051101 | MONTICELLO 1101 | Napa | 9 | 0.08057% | OH | 4.8887
INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | Mariposa | 10 | 0.08953% | Hybrid | 15.817 | 0.38714 | 2025
ANTLER 11011384 | 103271101 | ANTLER 1101 | Shasta | 11 | 0.09848% | UG | 9.0375 |  | 2025
MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | Lake | 13 | 0.1164% | Hybrid | 8.8255
SILVERADO 2104646776 | 43432104 | SILVERADO 2104 | Napa | 14 | 0.1253% |  | 3.5161 | 2.5897 | 2025
CLAYTON 221296224 | 12022212 | CLAYTON 2212 | Contra Costa | 15 | 0.1343% | Hybrid | 7.6836
ORO FINO 1102CB | 103031102 | ORO FINO 1102 | Butte | 17 | 0.1522% | Hybrid | 2.157 |  | 2025
BALCH NO 1 1101105414 | 252501101 | BALCH NO 1 1101 | Fresno | 18 | 0.1611% | OH | 6.9964 | 4.8871 | 2026
BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | Placer | 20 | 0.1791% | Hybrid | 14.4437 |  | 2020
BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | N/A | 21 | 0.188% | Hybrid | 4.8133
OAKHURST 110310140 | 254421103 | OAKHURST 1103 | Madera | 22 | 0.197% | Hybrid | 16.6046 |  | 2025
PARADISE 1103283794 | 102831103 | PARADISE 1103 | Butte | 23 | 0.2059% |  | 2.2274
CALISTOGA 1102131531 | 42711102 | CALISTOGA 1102 | Napa | 24 | 0.2149% | Hybrid | 4.8416 | 0.1616 | 2025
MONTICELLO 1101654 | 43051101 | MONTICELLO 1101 | Napa | 27 | 0.2417% | Hybrid | 8.5423 |  | 2026
ELECTRA 1102CB | 162161102 | ELECTRA 1102 | Amador | 28 | 0.2507% | OH | 2.6041 | 2.4821 | 2026
HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | Lake | 29 | 0.2596% | Hybrid | 14.7136
APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | El Dorado | 30 | 0.2686% | OH | 4.0817 |  | 2026
APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | El Dorado | 32 | 0.2865% | Hybrid | 12.1088 | 0.21135 | 2023
SILVERADO 2104515946 | 43432104 | SILVERADO 2104 | Napa | 33 | 0.2954% | Hybrid | 16.2604 | 1.9815 | 2026
CURTIS 170356972 | 163351703 | CURTIS 1703 | Tuolumne | 34 | 0.3044% | Hybrid | 8.2034 |  | 2025
UPPER LAKE 11011276 | 42871101 | UPPER LAKE 1101 | Lake | 35 | 0.3133% | Hybrid | 12.7917
FRENCH GULCH 1101CB | 103381101 | FRENCH GULCH 1101 | Shasta | 36 | 0.3223% | Hybrid | 2.3629 |  | 2025
NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | Butte | 37 | 0.3312% | Hybrid | 10.8392 |  | 2024
MIDDLETOWN 1101171414 | 43141101 | MIDDLETOWN 1101 | Lake | 38 | 0.3402% | UG | 3.5119 | 1.4984 | 2026
ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | Sierra | 41 | 0.3671% | Hybrid | 17.7807 |  | 2021
FRENCH GULCH 1102CB | 103381102 | FRENCH GULCH 1102 | Shasta | 42 | 0.376% | OH | 1.8226 | 0.082634 | 2026
KESWICK 11019712 | 103451101 | KESWICK 1101 | Shasta | 43 | 0.385% | Hybrid | 18.5915 | 0.48533 | 2025
REDBUD 1101454 | 43191101 | REDBUD 1101 | Lake | 44 | 0.3939% | Hybrid | 5.5315
BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | Plumas | 45 | 0.4029% | Hybrid | 29.4282
NARROWS 2102CB | 153132102 | NARROWS 2102 | Nevada | 46 | 0.4118% | OH | 5.08 |  | 2026
CLARK ROAD 110247006 | 103091102 | CLARK ROAD 1102 | Butte | 47 | 0.4208% | UG | 4.4768
KESWICK 11011586 | 103451101 | KESWICK 1101 | Shasta | 48 | 0.4297% | Hybrid | 7.4823
EL DORADO PH 210119752 | 152762101 | EL DORADO PH 2101 | El Dorado | 49 | 0.4387% | Hybrid | 38.5695
KONOCTI 11022293 | 43311102 | KONOCTI 1102 | Lake | 51 | 0.4566% | Hybrid | 1.7304 |  | 2026
PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | Sierra | 52 | 0.4655% | UG | 5.8943 |  | 2026
BEAR VALLEY 2105CB | 252192105 | BEAR VALLEY 2105 | Mariposa | 53 | 0.4745% | Hybrid | 16.0286 | 0.025529 | 2024
STANISLAUS 1702CB | 162821702 | STANISLAUS 1702 | Calaveras | 54 | 0.4834% | Hybrid | 8.1019
APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | El Dorado | 55 | 0.4924% |  | 5.4274 | 0.22205 | 2025
SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | Butte | 57 | 0.5103% | UG | 21.6869 | 2.8546 | 2025
PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | El Dorado | 58 | 0.5192% | UG | 20.7464 |  | 2021
SILVERADO 2104632 | 43432104 | SILVERADO 2104 | Napa | 59 | 0.5282% | UG | 18.385 |  | 2025
STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | Calaveras | 60 | 0.5372% | UG | 8.3079 | 1.6614 | 2026
ORO FINO 110276008 | 103031102 | ORO FINO 1102 | Butte | 61 | 0.5461% | Hybrid | 16.1491 | 1.8021 | 2025
ELECTRA 11017104 | 162161101 | ELECTRA 1101 | Amador | 62 | 0.5551% | Hybrid | 12.074 |  | 2024
APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | El Dorado | 63 | 0.564% | UG | 22.8336 |  | 2025
OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | Shasta | 64 | 0.573% | Hybrid | 13.1714 | 0.62271 | 2022
STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | Tuolumne | 66 | 0.5909% | Hybrid | 19.2034 |  | 2023
CURTIS 17039240 | 163351703 | CURTIS 1703 | Tuolumne | 67 | 0.5998% | UG | 10.8962 |  | 2026
PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | El Dorado | 68 | 0.6088% | Hybrid | 42.7004 |  | 2022
MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 70 | 0.6267% | Hybrid | 7.2944 | 0.50993 | 2023
SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | Placer | 71 | 0.6356% | Hybrid | 12.2854 |  | 2022
TEJON 11022455 | 252931102 | TEJON 1102 | Kern | 72 | 0.6446% | Hybrid | 6.319
GIRVAN 11029012 | 103401102 | GIRVAN 1102 | Shasta | 73 | 0.6535% | Hybrid | 15.5575 | 0.57454 | 2025
BRUNSWICK 1103639148 | 152481103 | BRUNSWICK 1103 | Nevada | 74 | 0.6625% |  | 8.9938
COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | Nevada | 75 | 0.6714% | Hybrid | 8.3716 | 0.26579 | 2021
BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | Mariposa | 76 | 0.6804% | Hybrid | 4.5851 |  | 2026
MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | Mariposa | 77 | 0.6893% | OH | 5.5893
CALISTOGA 1102141073 | 42711102 | CALISTOGA 1102 | Napa | 78 | 0.6983% |  | 2.1301
CALPINE 1146CB | 48011146 | CALPINE 1146 | Sonoma | 79 | 0.7073% |  | 2.9685
WEST POINT 11021341 | 163201102 | WEST POINT 1102 | Calaveras | 80 | 0.7162% | OH | 9.7908 | 0.98227 | 2025
EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | El Dorado | 81 | 0.7252% | Hybrid | 7.2823 |  | 2019
MARIPOSA 2101CB | 254452101 | MARIPOSA 2101 | Mariposa | 82 | 0.7341% | OH | 2.4592
KESWICK 11011588 | 103451101 | KESWICK 1101 | Shasta | 83 | 0.7431% | Hybrid | 8.7083 | 0.38648 | 2026
BALCH NO 1 1101406582 | 252501101 | BALCH NO 1 1101 | Fresno | 84 | 0.752% | OH | 3.6869 |  | 2025
ELK CREEK 11012032 | 102781101 | ELK CREEK 1101 | Glenn | 85 | 0.761% | OH | 9.3496 | 0.0099158 | 2026
WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | Trinity | 86 | 0.7699% | Hybrid | 7.7772
SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | Napa | 87 | 0.7789% | Hybrid | 16.8969 | 2.082 | 2019
SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | Placer | 89 | 0.7968% | Hybrid | 11.4113
ANTLER 11011520 | 103271101 | ANTLER 1101 | Shasta | 91 | 0.8147% | Hybrid | 8.9409 |  | 2024
MIWUK 170111800 | 163661701 | MIWUK 1701 | Tuolumne | 92 | 0.8236% |  | 9.5064
SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | Placer | 93 | 0.8326% | Hybrid | 19.7286 |  | 2022
ANTLER 1101CB | 103271101 | ANTLER 1101 | Shasta | 94 | 0.8415% | Hybrid | 1.5904 | 0.49778 | 2026
STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | Tuolumne | 95 | 0.8505% | Hybrid | 36.4691 | 0.61523 | 2023
PLACERVILLE 210692012 | 153082106 | PLACERVILLE 2106 | El Dorado | 96 | 0.8594% |  | 18.4325
FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | Placer | 97 | 0.8684% | Hybrid | 27.8705 |  | 2025
STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | Calaveras | 98 | 0.8774% | UG | 6.7927 |  | 2024
MIDDLETOWN 1101433160 | 43141101 | MIDDLETOWN 1101 | Lake | 99 | 0.8863% | UG | 1.5408
SILVERADO 210478268 | 43432104 | SILVERADO 2104 | Napa | 101 | 0.9042% | Hybrid | 11.4487
MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | Lake | 102 | 0.9132% | Hybrid | 28.1417
DRUM 1101CB | 152321101 | DRUM 1101 | Placer | 103 | 0.9221% | Hybrid | 2.1646 | 0.13059 | 2026
CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | Napa | 105 | 0.94% | Hybrid | 9.3913
WEST POINT 11014706 | 163201101 | WEST POINT 1101 | Amador | 107 | 0.9579% | Hybrid | 11.4709 | 0.034934 | 2025
BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | Butte | 108 | 0.9669% | Hybrid | 5.3451 | 2.2119 | 2019
WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | Trinity | 109 | 0.9758% | Hybrid | 5.0272 |  | 2026
WEST POINT 110277204 | 163201102 | WEST POINT 1102 | Calaveras | 110 | 0.9848% | Hybrid | 7.4433 | 0.027178 | 2026
WILDWOOD 1101384582 | 103611101 | WILDWOOD 1101 | Trinity | 111 | 0.9937% |  | 4.5387
COLUMBIA HILL 110135424 | 152471101 | COLUMBIA HILL 1101 | Nevada | 112 | 1.003% |  | 13.8934
SO. CAL. EDISON #3 1101CB | 258861101 | SO. CAL. EDISON #3 1101 | Fresno | 113 | 1.012% |  | 8.1187
FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | Placer | 114 | 1.021% | Hybrid | 11.6351 |  | 2024
CLAYTON 2212681608 | 12022212 | CLAYTON 2212 | Contra Costa | 115 | 1.03% | Hybrid | 26.818 |  | 2026
PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | Sierra | 116 | 1.038% | Hybrid | 19.67 |  | 2025
ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | Amador | 118 | 1.056% | Hybrid | 5.7665 | 0.50558 | 2025
KESWICK 110148480 | 103451101 | KESWICK 1101 | Shasta | 119 | 1.065% | Hybrid | 10.5204 | 0.10623 | 2026
SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | Placer | 120 | 1.074% | Hybrid | 8.0771 | 1.2888 | 2021
EL DORADO PH 2102542272 | 152762102 | EL DORADO PH 2102 | El Dorado | 121 | 1.083% |  | 7.7436
PEORIA 170190090 | 163781701 | PEORIA 1701 | Tuolumne | 122 | 1.092% | Hybrid | 29.8614
APPLE HILL 110413512 | 153661104 | APPLE HILL 1104 | El Dorado | 124 | 1.11% |  | 30.2001
BEAR VALLEY 21059570 | 252192105 | BEAR VALLEY 2105 | Mariposa | 125 | 1.119% | Hybrid | 7.9708 |  | 2024
MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | Mariposa | 126 | 1.128% | Hybrid | 19.8722 |  | 2023
REDBUD 1101323962 | 43191101 | REDBUD 1101 | Lake | 127 | 1.137% | Hybrid | 28.5898
ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | Sierra | 128 | 1.146% | Hybrid | 4.0965 |  | 2026
ORO FINO 11022236 | 103031102 | ORO FINO 1102 | Butte | 129 | 1.155% | Hybrid | 2.5364
PINE GROVE 11026080 | 163751102 | PINE GROVE 1102 | Amador | 131 | 1.173% |  | 34.3486
APPLE HILL 2102836878 | 153662102 | APPLE HILL 2102 | El Dorado | 132 | 1.182% | Hybrid | 40.8369
SALT SPRINGS 210297924 | 163692102 | SALT SPRINGS 2102 | Calaveras | 133 | 1.191% |  | 5.2013
CALISTOGA 1101122350 | 42711101 | CALISTOGA 1101 | Napa | 134 | 1.2% | Hybrid | 13.4533 | 1.2606 | 2025
KESWICK 11011590 | 103451101 | KESWICK 1101 | Shasta | 135 | 1.209% | OH | 6.2972 | 0.12601 | 2026
MARIPOSA 210110170 | 254452101 | MARIPOSA 2101 | Mariposa | 137 | 1.226% | Hybrid | 16.1371
COLUMBIA HILL 1101CB | 152471101 | COLUMBIA HILL 1101 | Nevada | 138 | 1.235% |  | 44.1613
PINE GROVE 11023172 | 163751102 | PINE GROVE 1102 | Amador | 139 | 1.244% | OH | 9.4625
ORO FINO 110265932 | 103031102 | ORO FINO 1102 | Butte | 140 | 1.253% |  | 11.2245
COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | Nevada | 141 | 1.262% | Hybrid | 8.4346
WEIMAR 11012084 | 152491101 | WEIMAR 1101 | Placer | 142 | 1.271% |  | 18.5776
ANTLER 11011612 | 103271101 | ANTLER 1101 | Shasta | 143 | 1.28% | Hybrid | 7.9154 |  | 2021
HIGHLANDS 1103726580 | 43361103 | HIGHLANDS 1103 | Lake | 144 | 1.289% | Hybrid | 8.5171 | 0.6353 | 2026
APPLE HILL 21029722 | 153662102 | APPLE HILL 2102 | El Dorado | 145 | 1.298% | OH | 38.1954
PINE GROVE 11013166 | 163751101 | PINE GROVE 1101 | Amador | 147 | 1.316% |  | 12.1497 | 10.3238 | 2024
PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | El Dorado | 148 | 1.325% | Hybrid | 12.9786 | 0.41562 | 2025
COLUMBIA HILL 1101764 | 152471101 | COLUMBIA HILL 1101 | Nevada | 149 | 1.334% | LR | 14.691
ORO FINO 11022090 | 103031102 | ORO FINO 1102 | Butte | 150 | 1.343% |  | 14.8409
TIGER CREEK 0201320746 | 161380201 | TIGER CREEK 0201 | Amador | 151 | 1.352% |  | 3.5158
KONOCTI 1102806668 | 43311102 | KONOCTI 1102 | Lake | 152 | 1.361% |  | 2.0853
WEST POINT 110236676 | 163201102 | WEST POINT 1102 | Calaveras | 154 | 1.379% |  | 16.6363
NOTRE DAME 1104176446 | 102041104 | NOTRE DAME 1104 | Butte | 155 | 1.388% | OH | 8.505 | 0.25199 | 2025
HIGHLANDS 1103287766 | 43361103 | HIGHLANDS 1103 | Lake | 156 | 1.397% | OH | 17.1622 |  | 2026
KANAKA 1101859138 | 103221101 | KANAKA 1101 | Butte | 157 | 1.406% |  | 6.2333
ORO FINO 1101CB | 103031101 | ORO FINO 1101 | Butte | 158 | 1.415% |  | 22.6501
MIDDLETOWN 1101959140 | 43141101 | MIDDLETOWN 1101 | Lake | 160 | 1.432% | OH | 3.9356 | 0.51574 | 2026
PINE GROVE 1102CB | 163751102 | PINE GROVE 1102 | Amador | 161 | 1.441% |  | 10.8158
PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | Sierra | 162 | 1.45% | Hybrid | 9.5167
WEST POINT 11024788 | 163201102 | WEST POINT 1102 | Calaveras | 164 | 1.468% | UG | 72.2384 | 68.94 | 2019
MOUNTAIN QUARRIES 21012422 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 165 | 1.477% |  | 8.5438
WEIMAR 11012058 | 152491101 | WEIMAR 1101 | Placer | 166 | 1.486% |  | 24.5192
APPLE HILL 210251792 | 153662102 | APPLE HILL 2102 | El Dorado | 167 | 1.495% |  | 9.257
HARTLEY 11014710 | 43211101 | HARTLEY 1101 | Lake | 168 | 1.504% |  | 1.5223
CALPINE 1144CB | 48011144 | CALPINE 1144 | Sonoma | 169 | 1.513% |  | 26.765
ALLEGHANY 1101CB | 152101101 | ALLEGHANY 1101 | Sierra | 170 | 1.522% |  | 4.3611
TULE POWER HOUSE 1101CB | 258591101 | TULE POWER HOUSE 1101 | Tulare | 171 | 1.531% |  | 4.0705
OAKHURST 11015490 | 254421101 | OAKHURST 1101 | Madera | 172 | 1.54% |  | 24.6359
MIDDLETOWN 1101439572 | 43141101 | MIDDLETOWN 1101 | Lake | 174 | 1.558% | Hybrid | 1.2561
MIDDLETOWN 1101352182 | 43141101 | MIDDLETOWN 1101 | Lake | 175 | 1.567% |  | 2.0574
EL DORADO PH 210219542 | 152762102 | EL DORADO PH 2102 | El Dorado | 176 | 1.576% |  | 9.4781
MOUNTAIN QUARRIES 210192474 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 177 | 1.585% |  | 15.3488
LOS OSITOS 21033010 | 182082103 | LOS OSITOS 2103 | Monterey | 178 | 1.594% |  | 30.0247
FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | Placer | 179 | 1.603% | UG | 22.1876
SHADY GLEN 1102CB | 152431102 | SHADY GLEN 1102 | Placer | 180 | 1.611% | Hybrid | 21.1169
ORO FINO 11022556 | 103031102 | ORO FINO 1102 | Butte | 181 | 1.62% | LR | 6.6456
MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | Lake | 182 | 1.629% | OH | 23.5712 | 19.496 | 2021
CALAVERAS CEMENT 11014786 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 184 | 1.647% | LR | 17.7888
MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | Lake | 185 | 1.656% | Hybrid | 18.3135
STANISLAUS 17011331 | 162821701 | STANISLAUS 1701 | Tuolumne | 186 | 1.665% |  | 4.3891
BIG BEND 1102CB | 103751102 | BIG BEND 1102 | Butte | 187 | 1.674% | OH | 17.3311
MONTICELLO 1101720 | 43051101 | MONTICELLO 1101 | Napa | 188 | 1.683% |  | 8.1324
HARTLEY 1101336932 | 43211101 | HARTLEY 1101 | Lake | 189 | 1.692% |  | 8.4794
APPLE HILL 11038412 | 153661103 | APPLE HILL 1103 | El Dorado | 190 | 1.701% | LR | 19.6178
WILDWOOD 11011576 | 103611101 | WILDWOOD 1101 | Trinity | 191 | 1.71% |  | 8.062
BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | Placer | 192 | 1.719% | UG | 34.0026
CORNING 110185152 | 103331101 | CORNING 1101 | Tehama | 194 | 1.737% | Hybrid | 23.071
EL DORADO PH 210219562 | 152762102 | EL DORADO PH 2102 | El Dorado | 195 | 1.746% | Hybrid | 2.8622
SHINGLE SPRINGS 2108CB | 153652108 | SHINGLE SPRINGS 2108 | El Dorado | 196 | 1.755% |  | 1.428
APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | El Dorado | 197 | 1.764% | Hybrid | 25.5648
CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 198 | 1.773% | Hybrid | 14.8876
MARIPOSA 2101752630 | 254452101 | MARIPOSA 2101 | Mariposa | 199 | 1.782% | Hybrid | 18.7528
CLEAR LAKE 1102904 | 42141102 | CLEAR LAKE 1102 | Lake | 200 | 1.791% |  | 3.5481
TASSAJARA 2112791386 | 14662112 | TASSAJARA 2112 | Contra Costa | 202 | 1.808% |  | 2.4112
SILVERADO 2104726 | 43432104 | SILVERADO 2104 | Napa | 203 | 1.817% | Hybrid | 33.6539
PINE GROVE 110213438 | 163751102 | PINE GROVE 1102 | Amador | 204 | 1.826% | Hybrid | 16.5261 | 11.8755 | 2024
BEAR VALLEY 2101CB | 252192101 | BEAR VALLEY 2101 | Mariposa | 205 | 1.835% |  | 18.1114
WEST POINT 11021305 | 163201102 | WEST POINT 1102 | Calaveras | 206 | 1.844% |  | 11.3098
WISHON 1101CB | 251511101 | WISHON 1101 | Madera | 207 | 1.853% |  | 7.553
SHADY GLEN 110151696 | 152431101 | SHADY GLEN 1101 | Placer | 208 | 1.862% |  | 18.3265
GIRVAN 11019732 | 103401101 | GIRVAN 1101 | Shasta | 209 | 1.871% | LR | 20.9965
ANTLER 11011376 | 103271101 | ANTLER 1101 | Shasta | 210 | 1.88% |  | 9.175
MIDDLETOWN 1101614 | 43141101 | MIDDLETOWN 1101 | Lake | 211 | 1.889% |  | 1.3822
KANAKA 1101CB | 103221101 | KANAKA 1101 | Butte | 212 | 1.898% | Hybrid | 41.2802
WEST POINT 11024790 | 163201102 | WEST POINT 1102 | Calaveras | 213 | 1.907% |  | 32.5359
WEIMAR 1101CB | 152491101 | WEIMAR 1101 | Placer | 214 | 1.916% | OH | 9.2257
MOUNTAIN QUARRIES 21011180 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 215 | 1.925% |  | 12.9561
MIWUK 17021808 | 163661702 | MIWUK 1702 | Tuolumne | 216 | 1.934% | UG | 1.8076 | 0.25634 | 2023
CALAVERAS CEMENT 11012646 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 217 | 1.943% | LR | 17.5628
WEST POINT 1101CB | 163201101 | WEST POINT 1101 | Amador | 218 | 1.952% | Hybrid | 4.7928
TEJON 1102732836 | 252931102 | TEJON 1102 | Kern | 219 | 1.961% | Hybrid | 15.5796 |  | 2021
STILLWATER 11021466 | 103561102 | STILLWATER 1102 | Shasta | 220 | 1.97% | UG | 20.397
BUTTE 1105398234 | 103081105 | BUTTE 1105 | Butte | 221 | 1.979% |  | 15.0803
LUCERNE 1103245134 | 43351103 | LUCERNE 1103 | Lake | 222 | 1.987% |  | 5.0029
CLAYTON 2212204416 | 12022212 | CLAYTON 2212 | Contra Costa | 223 | 1.996% |  | 11.7586
SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 225 | 2.014% | Hybrid | 18.052
FROGTOWN 170113412 | 163451701 | FROGTOWN 1701 | Calaveras | 226 | 2.023% |  | 38.8027
FRENCH GULCH 11012905 | 103381101 | FRENCH GULCH 1101 | Shasta | 227 | 2.032% |  | 9.5145
TEMPLETON 2113A10 | 183052113 | TEMPLETON 2113 | San Luis Obispo | 228 | 2.041% |  | 30.7752
PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | El Dorado | 230 | 2.059% | Hybrid | 6.4582
STANISLAUS 170179826 | 162821701 | STANISLAUS 1701 | Tuolumne | 231 | 2.068% |  | 10.1921
FORESTHILL 1101CB | 152181101 | FORESTHILL 1101 | Placer | 232 | 2.077% | UG | 9.0779
PINE GROVE 110245292 | 163751102 | PINE GROVE 1102 | Amador | 233 | 2.086% | UG | 10.7857 | 0.72206 | 2026
BRUNSWICK 11021010 | 152481102 | BRUNSWICK 1102 | Nevada | 234 | 2.095% |  | 44.5228
BALCH NO 1 1101R372 | 252501101 | BALCH NO 1 1101 | Fresno | 235 | 2.104% | OH | 3.8992
PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | El Dorado | 236 | 2.113% | UG | 24.6861
SHINGLE SPRINGS 210911092 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 237 | 2.122% | LR | 22.0883
CALPINE 1144960 | 48011144 | CALPINE 1144 | Sonoma | 238 | 2.131% |  | 4.0614
BEAR VALLEY 2105293732 | 252192105 | BEAR VALLEY 2105 | Mariposa | 239 | 2.14% |  | 26.0604
PINE GROVE 110194936 | 163751101 | PINE GROVE 1101 | Amador | 240 | 2.149% |  | 9.1551
SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 241 | 2.158% | Hybrid | 11.3804
MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | Mariposa | 242 | 2.167% |  | 19.5831
WEST POINT 110272036 | 163201102 | WEST POINT 1102 | Calaveras | 243 | 2.175% |  | 13.1539
BIG BEND 1101CB | 103751101 | BIG BEND 1101 | Butte | 244 | 2.184% | Hybrid | 23.1433
BANGOR 1101626862 | 103191101 | BANGOR 1101 | Yuba | 245 | 2.193% |  | 11.2783
ANTLER 11011378 | 103271101 | ANTLER 1101 | Shasta | 247 | 2.211% |  | 24.904
GRASS VALLEY 11012208 | 152031101 | GRASS VALLEY 1101 | Nevada | 248 | 2.22% |  | 12.8805
MARIPOSA 2101151918 | 254452101 | MARIPOSA 2101 | Mariposa | 249 | 2.229% |  | 16.5872
WYANDOTTE 1103640652 | 102911103 | WYANDOTTE 1103 | Butte | 250 | 2.238% |  | 34.4733
ELECTRA 1101CB | 162161101 | ELECTRA 1101 | Amador | 251 | 2.247% | UG | 23.2606
PUTAH CREEK 110264044 | 63681102 | PUTAH CREEK 1102 | Yolo | 252 | 2.256% | OH | 7.4872
PEORIA 170169124 | 163781701 | PEORIA 1701 | Tuolumne | 253 | 2.265% |  | 2.6937
ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | Sierra | 254 | 2.274% | Hybrid | 11.3077
PUEBLO 2103678 | 43292103 | PUEBLO 2103 | Napa | 255 | 2.283% | Hybrid | 33.1561
WEST POINT 110113444 | 163201101 | WEST POINT 1101 | Amador | 256 | 2.292% | OH | 27.7558
RINCON 11035152 | 43321103 | RINCON 1103 | Sonoma | 257 | 2.301% | OH | 1.6684
CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 260 | 2.328% |  | 17.211
MONTICELLO 11011589 | 43051101 | MONTICELLO 1101 | Napa | 261 | 2.337% |  | 4.2252
FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | Shasta | 262 | 2.346% | Hybrid | 7.023
BEAR VALLEY 21054170 | 252192105 | BEAR VALLEY 2105 | Mariposa | 263 | 2.355% | UG | 9.3206
PUEBLO 2103355186 | 43292103 | PUEBLO 2103 | Napa | 264 | 2.363% |  | 1.8362
TEMPLETON 2113A12 | 183052113 | TEMPLETON 2113 | San Luis Obispo | 265 | 2.372% | LR | 40.801
BRUNSWICK 110651484 | 152481106 | BRUNSWICK 1106 | Nevada | 266 | 2.381% |  | 24.4319
BIG BEND 1102884340 | 103751102 | BIG BEND 1102 | Butte | 267 | 2.39% |  | 20.9221
WEIMAR 11012764 | 152491101 | WEIMAR 1101 | Placer | 268 | 2.399% |  | 6.2203
STANISLAUS 17017144 | 162821701 | STANISLAUS 1701 | Tuolumne | 269 | 2.408% |  | 4.639
HIGHLANDS 1103917328 | 43361103 | HIGHLANDS 1103 | Lake | 270 | 2.417% |  | 8.8059
FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | Shasta | 271 | 2.426% | Hybrid | 3.234
WEIMAR 11012740 | 152491101 | WEIMAR 1101 | Placer | 272 | 2.435% |  | 15.6695
ORO FINO 110239154 | 103031102 | ORO FINO 1102 | Butte | 273 | 2.444% | LR | 42.1729 | 40.279 | 2026
SISQUOC 1102M52 | 182811102 | SISQUOC 1102 | Santa Barbara | 274 | 2.453% |  | 35.2771
MOUNTAIN QUARRIES 21011184 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 275 | 2.462% | LR | 11.4188
SWIFT 2110XR332 | 83392110 | SWIFT 2110 | Santa Clara | 276 | 2.471% | OH | 18.463
PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | El Dorado | 277 | 2.48% | UG | 67.3979
EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | El Dorado | 278 | 2.489% | UG | 5.5262
MARTELL 110191216 | 163011101 | MARTELL 1101 | Amador | 279 | 2.498% |  | 40.2681
VOLTA 110153118 | 102541101 | VOLTA 1101 | Tehama | 280 | 2.507% | OH | 9.6029
VOLTA 11011596 | 102541101 | VOLTA 1101 | Tehama | 281 | 2.516% | Hybrid | 21.6979
DOBBINS 110169722 | 153741101 | DOBBINS 1101 | Yuba | 282 | 2.525% | UG | 6.5279
MIWUK 170193062 | 163661701 | MIWUK 1701 | Tuolumne | 283 | 2.534% |  | 7.8055
APPLE HILL 1103CB | 153661103 | APPLE HILL 1103 | El Dorado | 284 | 2.543% | LR | 22.8514
BRUNSWICK 11052130 | 152481105 | BRUNSWICK 1105 | Nevada | 286 | 2.56% |  | 11.5892
EL DORADO PH 210119612 | 152762101 | EL DORADO PH 2101 | El Dorado | 287 | 2.569% | UG | 8.6815
ELECTRA 110136816 | 162161101 | ELECTRA 1101 | Amador | 288 | 2.578% |  | 4.9856
TEMPLETON 2113641367 | 183052113 | TEMPLETON 2113 | San Luis Obispo | 289 | 2.587% |  | 39.0256
NOTRE DAME 11042537 | 102041104 | NOTRE DAME 1104 | Butte | 290 | 2.596% |  | 4.8784
SILVERADO 2105247660 | 43432105 | SILVERADO 2105 | Napa | 291 | 2.605% |  | 3.246
WYANDOTTE 1107829470 | 102911107 | WYANDOTTE 1107 | Butte | 292 | 2.614% |  | 10.3312
PEORIA 1701169700 | 163781701 | PEORIA 1701 | Tuolumne | 293 | 2.623% |  | 8.3152
BRUNSWICK 1105875388 | 152481105 | BRUNSWICK 1105 | Nevada | 294 | 2.632% |  | 2.9513
CALAVERAS CEMENT 110180930 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 295 | 2.641% | LR | 17.8564
CURTIS 170390320 | 163351703 | CURTIS 1703 | Tuolumne | 296 | 2.65% |  | 27.8854
KONOCTI 110264664 | 43311102 | KONOCTI 1102 | Lake | 297 | 2.659% |  | 26.668
CALISTOGA 11015934 | 42711101 | CALISTOGA 1101 | Napa | 299 | 2.677% |  | 25.7753
APPLE HILL 21021532 | 153662102 | APPLE HILL 2102 | El Dorado | 300 | 2.686% |  | 41.8821
PIKE CITY 11011730 | 152201101 | PIKE CITY 1101 | Sierra | 301 | 2.695% |  | 8.4704
PINE GROVE 11023168 | 163751102 | PINE GROVE 1102 | Amador | 303 | 2.713% |  | 29.9753
PLACERVILLE 21062224 | 153082106 | PLACERVILLE 2106 | El Dorado | 304 | 2.722% |  | 10.3969
PLACERVILLE 210619552 | 153082106 | PLACERVILLE 2106 | El Dorado | 305 | 2.731% |  | 21.378
WEST POINT 1102CB | 163201102 | WEST POINT 1102 | Calaveras | 306 | 2.739% | Hybrid | 22.4117
WEST POINT 110234416 | 163201102 | WEST POINT 1102 | Calaveras | 307 | 2.748% | LR | 25.7664
ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | Glenn | 308 | 2.757% | LR | 13.1577
UPPER LAKE 110175370 | 42871101 | UPPER LAKE 1101 | Lake | 309 | 2.766% |  | 17.1753
PINE GROVE 11011021 | 163751101 | PINE GROVE 1101 | Amador | 310 | 2.775% |  | 4.165
PASO ROBLES 1103N52 | 182611103 | PASO ROBLES 1103 | San Luis Obispo | 311 | 2.784% | OH | 6.569
JAMESON 110265516 | 63801102 | JAMESON 1102 | Solano | 313 | 2.802% | Hybrid | 11.2949
BRUNSWICK 110651486 | 152481106 | BRUNSWICK 1106 | Nevada | 315 | 2.82% |  | 56.752
PIT NO 5 11011614 | 101321101 | PIT NO 5 1101 | Shasta | 316 | 2.829% | OH | 1.8419
BIG BEND 1101641808 | 103751101 | BIG BEND 1101 | Butte | 318 | 2.847% | Hybrid | 28.6377
HIGGINS 1110166282 | 152691110 | HIGGINS 1110 | Nevada | 319 | 2.856% |  | 23.6133
COVELO 1101516510 | 43061101 | COVELO 1101 | Mendocino | 320 | 2.865% |  | 8.4329
CALAVERAS CEMENT 1101502 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 321 | 2.874% | LR | 40.703
FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | Placer | 322 | 2.883% | UG | 11.5935 | 9.1566 | 2022
AUBERRY 110137536 | 254151101 | AUBERRY 1101 | Fresno | 323 | 2.892% | OH | 3.4218
CURTIS 170411290 | 163351704 | CURTIS 1704 | Tuolumne | 325 | 2.91% |  | 7.8564
PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | Shasta | 326 | 2.919% | Hybrid | 4.5495 |  | 2025
UPPER LAKE 1101412 | 42871101 | UPPER LAKE 1101 | Lake | 327 | 2.927% | LR | 17.429
PLACERVILLE 1109868678 | 153081109 | PLACERVILLE 1109 | El Dorado | 328 | 2.936% |  | 10.9807
MIWUK 1701767890 | 163661701 | MIWUK 1701 | Tuolumne | 329 | 2.945% |  | 11.8268
MONTICELLO 1101256640 | 43051101 | MONTICELLO 1101 | Napa | 330 | 2.954% |  | 10.4771
CALAVERAS CEMENT 1101544800 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 331 | 2.963% | Hybrid | 22.9909
KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | Lake | 332 | 2.972% | Hybrid | 2.6765
COARSEGOLD 210410110 | 254432104 | COARSEGOLD 2104 | Madera | 333 | 2.981% |  | 49.2754
SHINGLE SPRINGS 210985766 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 336 | 3.008% |  | 18.517
SANTA YNEZ 1101980192 | 182721101 | SANTA YNEZ 1101 | Santa Barbara | 337 | 3.017% | OH | 3.8797
PUEBLO 2102378860 | 43292102 | PUEBLO 2102 | Napa | 338 | 3.026% |  | 20.1907
HIGGINS 11044281 | 152691104 | HIGGINS 1104 | Nevada | 339 | 3.035% |  | 13.3553
GIRVAN 11011636 | 103401101 | GIRVAN 1101 | Shasta | 340 | 3.044% |  | 18.3837
HALSEY 1102CB | 152241102 | HALSEY 1102 | Placer | 341 | 3.053% |  | 14.4793
DOBBINS 11011264 | 153741101 | DOBBINS 1101 | Yuba | 343 | 3.071% |  | 27.561
GIRVAN 11011330 | 103401101 | GIRVAN 1101 | Shasta | 345 | 3.089% | OH | 30.9852
SILVERADO 2103920793 | 43432103 | SILVERADO 2103 | Napa | 346 | 3.098% |  | 7.9849
CALPELLA 1101908688 | 43411101 | CALPELLA 1101 | Mendocino | 347 | 3.107% |  | 9.4603
AUBERRY 1101R324 | 254151101 | AUBERRY 1101 | Fresno | 348 | 3.115% | OH | 24.4374
FRENCH GULCH 11021462 | 103381102 | FRENCH GULCH 1102 | Shasta | 349 | 3.124% |  | 9.8869
STELLING 111060090 | 83481110 | STELLING 1110 | Santa Clara | 350 | 3.133% |  | 6.525
EL DORADO PH 210113532 | 152762101 | EL DORADO PH 2101 | El Dorado | 351 | 3.142% |  | 5.42
WEST POINT 110112256 | 163201101 | WEST POINT 1101 | Amador | 352 | 3.151% | UG | 6.5391 |  | 2025
UKIAH 1113548420 | 42771113 | UKIAH 1113 | Mendocino | 353 | 3.16% |  | 5.1738
ELECTRA 110161816 | 162161101 | ELECTRA 1101 | Amador | 355 | 3.178% |  | 23.4847
MONTICELLO 1101718 | 43051101 | MONTICELLO 1101 | Napa | 356 | 3.187% |  | 29.3286
MONTICELLO 110152910 | 43051101 | MONTICELLO 1101 | Napa | 358 | 3.205% |  | 3.1422
BUTTE 1105612016 | 103081105 | BUTTE 1105 | Butte | 360 | 3.223% |  | 5.4167
MONTICELLO 1101666 | 43051101 | MONTICELLO 1101 | Napa | 361 | 3.232% | OH | 13.5051
MIWUK 170238218 | 163661702 | MIWUK 1702 | Tuolumne | 363 | 3.25% |  | 14.4348
ARBUCKLE 1104669720 | 62081104 | ARBUCKLE 1104 | Colusa | 365 | 3.268% |  | 4.866
MONTICELLO 110193384 | 43051101 | MONTICELLO 1101 | Napa | 366 | 3.277% | OH | 17.2515
ELECTRA 11024756 | 162161102 | ELECTRA 1102 | Amador | 367 | 3.286% |  | 9.5967
TEJON 11023751 | 252931102 | TEJON 1102 | Kern | 368 | 3.295% | UG | 9.2397 | 1.8809 | 2021
CUYAMA 1103684566 | 253141103 | CUYAMA 1103 | San Luis Obispo | 369 | 3.303% |  | 3.0278
EL DORADO PH 210163464 | 152762101 | EL DORADO PH 2101 | El Dorado | 370 | 3.312% |  | 13.7502
SAN JOAQUIN #3 1101CB | 252531101 | SAN JOAQUIN #3 1101 | Madera | 371 | 3.321% |  | 5.1632
PLACERVILLE 1110953474 | 153081110 | PLACERVILLE 1110 | El Dorado | 372 | 3.33% |  | 10.7893
RACETRACK 170311270 | 163761703 | RACETRACK 1703 | Tuolumne | 373 | 3.339% |  | 12.4632
CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | Sonoma | 374 | 3.348% | Hybrid | 22.2289
REDBUD 1101754544 | 43191101 | REDBUD 1101 | Lake | 375 | 3.357% |  | 9.1433
DIAMOND SPRINGS 11057722 | 152261105 | DIAMOND SPRINGS 1105 | El Dorado | 376 | 3.366% | LR | 61.4374
PEORIA 1704877670 | 163781704 | PEORIA 1704 | Calaveras | 377 | 3.375% | OH | 6.4384
BRUNSWICK 11062790 | 152481106 | BRUNSWICK 1106 | Nevada | 378 | 3.384% | Hybrid | 9.6827
STANISLAUS 17021888 | 162821702 | STANISLAUS 1702 | Calaveras | 379 | 3.393% | UG | 18.9786
MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 380 | 3.402% | UG | 19.9125
SHINGLE SPRINGS 210961892 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 381 | 3.411% |  | 30.0462
VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | Solano | 383 | 3.429% | Hybrid | 15.3394
WEST POINT 110293116 | 163201102 | WEST POINT 1102 | Calaveras | 384 | 3.438% | LR | 42.2884
RINCON 1103925054 | 43321103 | RINCON 1103 | Sonoma | 385 | 3.447% |  | 11.9402
TEJON 11023760 | 252931102 | TEJON 1102 | Kern | 387 | 3.465% | OH | 6.4769
CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | Napa | 389 | 3.483% | Hybrid | 3.0901
DUNBAR 1102694641 | 43071102 | DUNBAR 1102 | Sonoma | 391 | 3.5% |  | 3.9951
MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | Lake | 392 | 3.509% | Hybrid | 5.7365
PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | Shasta | 394 | 3.527% | UG | 12.1398
REDBUD 1101CB | 43191101 | REDBUD 1101 | Lake | 395 | 3.536% | UG | 7.2989
OAKHURST 11035480 | 254421103 | OAKHURST 1103 | Madera | 396 | 3.545% |  | 16.8067
PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | El Dorado | 397 | 3.554% |  | 49.2341
SILVERADO 2105167360 | 43432105 | SILVERADO 2105 | Napa | 398 | 3.563% | OH | 9.5243 |  | 2022
CURTIS 17039210 | 163351703 | CURTIS 1703 | Tuolumne | 399 | 3.572% |  | 21.7808
MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | Mariposa | 400 | 3.581% | OH | 43.1986
MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 401 | 3.59% | Hybrid | 21.7138
PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | Shasta | 402 | 3.599% | UG | 4.5603
CURTIS 170234426 | 163351702 | CURTIS 1702 | Tuolumne | 403 | 3.608% |  | 6.7934
BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | Plumas | 404 | 3.617% | Hybrid | 2.1814
JOLON 11027040 | 182981102 | JOLON 1102 | Monterey | 405 | 3.626% |  | 22.6167
REDBUD 1102523244 | 43191102 | REDBUD 1102 | Lake | 407 | 3.644% |  | 19.1015
CHALLENGE 11025462 | 103201102 | CHALLENGE 1102 | Yuba | 408 | 3.653% | LR | 23.2454
BEAR VALLEY 210513430 | 252192105 | BEAR VALLEY 2105 | Mariposa | 409 | 3.662% |  | 12.8151
PINE GROVE 11013170 | 163751101 | PINE GROVE 1101 | Amador | 410 | 3.671% |  | 39.8105
CALISTOGA 1101886282 | 42711101 | CALISTOGA 1101 | Napa | 411 | 3.679% | OH | 10.8643
DIAMOND SPRINGS 110676088 | 152261106 | DIAMOND SPRINGS 1106 | El Dorado | 412 | 3.688% | LR | 32.3939
PLACERVILLE 210623190 | 153082106 | PLACERVILLE 2106 | El Dorado | 413 | 3.697% |  | 3.5347
BUTTE 1105235788 | 103081105 | BUTTE 1105 | Butte | 414 | 3.706% |  | 7.9849
MONTICELLO 110137384 | 43051101 | MONTICELLO 1101 | Napa | 415 | 3.715% | OH | 9.3362
LOS GATOS 1106697500 | 82021106 | LOS GATOS 1106 | Santa Clara | 417 | 3.733% |  | 6.7775
CURTIS 17048140 | 163351704 | CURTIS 1704 | Tuolumne | 418 | 3.742% | LR | 35.6796
PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | Shasta | 420 | 3.76% | Hybrid | 2.5579 | 0.30462 | 2024
DIAMOND SPRINGS 110656026 | 152261106 | DIAMOND SPRINGS 1106 | El Dorado | 421 | 3.769% |  | 14.6792
PUTAH CREEK 110267858 | 63681102 | PUTAH CREEK 1102 | Yolo | 423 | 3.787% | Hybrid | 11.2878
STELLING 11109265 | 83481110 | STELLING 1110 | Santa Clara | 424 | 3.796% | Hybrid | 5.4912
MONTICELLO 11014360 | 43051101 | MONTICELLO 1101 | Napa | 425 | 3.805% |  | 9.2878
RINCON 1103655192 | 43321103 | RINCON 1103 | Sonoma | 426 | 3.814% |  | 3.9474
SWIFT 2110853720 | 83392110 | SWIFT 2110 | Santa Clara | 427 | 3.823% |  | 30.4124
CALISTOGA 1101257964 | 42711101 | CALISTOGA 1101 | Napa | 428 | 3.832% |  | 16.2586
BRUNSWICK 11062104 | 152481106 | BRUNSWICK 1106 | Nevada | 429 | 3.841% |  | 9.6082
LUCERNE 11034200 | 43351103 | LUCERNE 1103 | Lake | 430 | 3.85% |  | 4.9035
KONOCTI 110275382 | 43311102 | KONOCTI 1102 | Lake | 431 | 3.859% | LR | 23.4088
CALPELLA 1101619542 | 43411101 | CALPELLA 1101 | Mendocino | 432 | 3.868% | Hybrid | 1.4872
BEAR VALLEY 210521160 | 252192105 | BEAR VALLEY 2105 | Mariposa | 433 | 3.876% | Hybrid | 22.9632
SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | Butte | 434 | 3.885% | Hybrid | 22.393 | 12.0637 | 2022
SILVERADO 2104722 | 43432104 | SILVERADO 2104 | Napa | 435 | 3.894% | Hybrid | 7.7922
APPLE HILL 2102186912 | 153662102 | APPLE HILL 2102 | El Dorado | 436 | 3.903% |  | 60.4176
MARTELL 110111244 | 163011101 | MARTELL 1101 | Amador | 437 | 3.912% |  | 21.5189
KONOCTI 1102948 | 43311102 | KONOCTI 1102 | Lake | 438 | 3.921% |  | 7.9446
COARSEGOLD 210210050 | 254432102 | COARSEGOLD 2102 | Madera | 439 | 3.93% |  | 7.061
DUNBAR 1101534 | 43071101 | DUNBAR 1101 | Sonoma | 440 | 3.939% |  | 17.232
BEAR VALLEY 21014160 | 252192101 | BEAR VALLEY 2101 | Mariposa | 441 | 3.948% |  | 22.8172
RACETRACK 1703CB | 163761703 | RACETRACK 1703 | Tuolumne | 442 | 3.957% |  | 18.1121
MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | Lake | 443 | 3.966% | Hybrid | 39.0621
ATASCADERO 1103A14 | 182541103 | ATASCADERO 1103 | San Luis Obispo | 444 | 3.975% |  | 25.246
CURTIS 17028000 | 163351702 | CURTIS 1702 | Tuolumne | 445 | 3.984% | Hybrid | 14.1863
LOW GAP 1101449990 | 192411101 | LOW GAP 1101 | Trinity | 446 | 3.993% |  | 3.9824
TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | Contra Costa | 448 | 4.011% | UG | 3.8711
RACETRACK 170310870 | 163761703 | RACETRACK 1703 | Tuolumne | 449 | 4.02% |  | 2.4884
DIAMOND SPRINGS 110519910 | 152261105 | DIAMOND SPRINGS 1105 | El Dorado | 450 | 4.029% |  | 20.594
COVELO 1101112804 | 43061101 | COVELO 1101 | Mendocino | 451 | 4.038% |  | 19.083
CHALLENGE 11015460 | 103201101 | CHALLENGE 1101 | Yuba | 452 | 4.047% |  | 31.8409
OAKHURST 110377384 | 254421103 | OAKHURST 1103 | Madera | 453 | 4.056% |  | 4.7055
RINCON 1103474 | 43321103 | RINCON 1103 | Sonoma | 454 | 4.064% | OH | 6.4053
CAMP EVERS 210511010 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 455 | 4.073% |  | 2.1786
TEMPLETON 2110N30 | 183052110 | TEMPLETON 2110 | San Luis Obispo | 456 | 4.082% |  | 19.7776
KERCKHOFF 1101R308 | 252561101 | KERCKHOFF 1101 | Fresno | 457 | 4.091% |  | 3.7523
CURTIS 170510590 | 163351705 | CURTIS 1705 | Tuolumne | 458 | 4.1% |  | 16.1136
LOS OSITOS 2102258878 | 182082102 | LOS OSITOS 2102 | Monterey | 459 | 4.109% |  | 4.322
RINCON 1103568 | 43321103 | RINCON 1103 | Sonoma | 460 | 4.118% | Hybrid | 8.6721
RACETRACK 170455798 | 163761704 | RACETRACK 1704 | Tuolumne | 461 | 4.127% | Hybrid | 22.9733
LOS COCHES 1101625902 | 182151101 | LOS COCHES 1101 | Monterey | 462 | 4.136% |  | 5.6071
APPLE HILL 21028372 | 153662102 | APPLE HILL 2102 | El Dorado | 463 | 4.145% | LR | 62.6502
CHALLENGE 1102CB | 103201102 | CHALLENGE 1102 | Yuba | 465 | 4.163% |  | 15.3136
CURTIS 17039330 | 163351703 | CURTIS 1703 | Tuolumne | 467 | 4.181% |  | 40.7469
DUNLAP 11037170 | 254061103 | DUNLAP 1103 | Fresno | 468 | 4.19% |  | 5.0285
BRUNSWICK 11062416 | 152481106 | BRUNSWICK 1106 | Nevada | 469 | 4.199% |  | 34.593
POTTER VALLEY P H 1105640888 | 42281105 | POTTER VALLEY P H 1105 | Mendocino | 470 | 4.208% |  | 8.5868
MOUNTAIN QUARRIES 21011102 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 472 | 4.226% |  | 43.1516
GIRVAN 1101323094 | 103401101 | GIRVAN 1101 | Shasta | 473 | 4.235% | OH | 34.5865
MOUNTAIN QUARRIES 21011346 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 474 | 4.244% |  | 30.8507
ALHAMBRA 1105295792 | 14101105 | ALHAMBRA 1105 | Contra Costa | 475 | 4.252% |  | 2.8805
LOS GATOS 1107914254 | 82021107 | LOS GATOS 1107 | Santa Clara | 476 | 4.261% |  | 1.172
CLARK ROAD 110290548 | 103091102 | CLARK ROAD 1102 | Butte | 477 | 4.27% | LR | 17.8017
KONOCTI 1102532 | 43311102 | KONOCTI 1102 | Lake | 478 | 4.279% | Hybrid | 7.491
JESSUP 110141356 | 103441101 | JESSUP 1101 | Shasta | 479 | 4.288% | LR | 32.4205
CALISTOGA 1101242919 | 42711101 | CALISTOGA 1101 | Napa | 480 | 4.297% |  | 1.312
HALSEY 110239104 | 152241102 | HALSEY 1102 | Placer | 481 | 4.306% |  | 30.673
DUNLAP 11027050 | 254061102 | DUNLAP 1102 | Fresno | 482 | 4.315% | LR | 12.66
SILVERADO 210234959 | 43432102 | SILVERADO 2102 | Napa | 483 | 4.324% | OH | 26.3601
MARIPOSA 210237282 | 254452102 | MARIPOSA 2102 | Mariposa | 484 | 4.333% | LR | 58.7539
SAN JOAQUIN #3 110110060 | 252531101 | SAN JOAQUIN #3 1101 | Madera | 485 | 4.342% |  | 6.5479
HARTLEY 1101698 | 43211101 | HARTLEY 1101 | Lake | 486 | 4.351% |  | 10.6191
MARIPOSA 210190180 | 254452101 | MARIPOSA 2101 | Mariposa | 487 | 4.36% |  | 4.8788
LAURELES 11116617 | 182371111 | LAURELES 1111 | Monterey | 488 | 4.369% |  | 1.7797
HIGGINS 11041374 | 152691104 | HIGGINS 1104 | Nevada | 489 | 4.378% |  | 8.273
VACAVILLE 110838316 | 63601108 | VACAVILLE 1108 | Solano | 491 | 4.396% | Hybrid | 22.9879
SAN JOAQUIN #3 11035100 | 252531103 | SAN JOAQUIN #3 1103 | Madera | 492 | 4.405% | OH | 25.8561
KANAKA 110183288 | 103221101 | KANAKA 1101 | Butte | 493 | 4.414% |  | 17.3082
SANTA YNEZ 1101Y52 | 182721101 | SANTA YNEZ 1101 | Santa Barbara | 495 | 4.432% |  | 20.4198
SAN JOAQUIN #3 110210342 | 252531102 | SAN JOAQUIN #3 1102 | Madera | 496 | 4.44% |  | 1.7906
DIAMOND SPRINGS 11062100 | 152261106 | DIAMOND SPRINGS 1106 | El Dorado | 498 | 4.458% |  | 38.1846
FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | Calaveras | 499 | 4.467% |  | 15.2038
DUNBAR 1102528 | 43071102 | DUNBAR 1102 | Sonoma | 500 | 4.476% |  | 4.0235
CLEAR LAKE 1101406 | 42141101 | CLEAR LAKE 1101 | Lake | 502 | 4.494% | LR | 32.9936
MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | Mariposa | 504 | 4.512% | UG | 62.3092
SAN JOAQUIN #2 1103157026 | 252521103 | SAN JOAQUIN #2 1103 | Madera | 505 | 4.521% |  | 3.1855
CALAVERAS CEMENT 110111188 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 506 | 4.53% |  | 29.9323
DUNLAP 1102CB | 254061102 | DUNLAP 1102 | Fresno | 507 | 4.539% |  | 6.6295
LOS GATOS 1107CB | 82021107 | LOS GATOS 1107 | Santa Clara | 508 | 4.548% |  | 14.1093
JOLON 1103CB | 182981103 | JOLON 1103 | Monterey | 509 | 4.557% |  | 18.5216
LAYTONVILLE 11022502 | 42681102 | LAYTONVILLE 1102 | Mendocino | 510 | 4.566% |  | 17.5791
POSO MOUNTAIN 2101CB | 253642101 | POSO MOUNTAIN 2101 | Kern | 511 | 4.575% |  | 4.3358
CORNING 11021622 | 103331102 | CORNING 1102 | Tehama | 512 | 4.584% |  | 33.6775
PEORIA 17051834 | 163781705 | PEORIA 1705 | Tuolumne | 513 | 4.593% |  | 23.3416
KONOCTI 1108950 | 43311108 | KONOCTI 1108 | Lake | 514 | 4.602% |  | 7.4086
LOS OSITOS 21037062 | 182082103 | LOS OSITOS 2103 | Monterey | 516 | 4.62% |  | 12.1456
DUNLAP 11037220 | 254061103 | DUNLAP 1103 | Fresno | 517 | 4.628% |  | 25.156
GRASS VALLEY 11032110 | 152031103 | GRASS VALLEY 1103 | Nevada | 518 | 4.637% |  | 19.6684
HOPLAND 1101768 | 42251101 | HOPLAND 1101 | Mendocino | 519 | 4.646% | LR | 19.6589
MORGAN HILL 2111123422 | 83242111 | MORGAN HILL 2111 | Santa Clara | 520 | 4.655% |  | 1.3237
GRAYS FLAT 0401CB | 102530401 | GRAYS FLAT 0401 | Plumas | 521 | 4.664% | Hybrid | 10.6401
HOPLAND 11014626 | 42251101 | HOPLAND 1101 | Mendocino | 522 | 4.673% |  | 31.1609
ELECTRA 11026014 | 162161102 | ELECTRA 1102 | Amador | 523 | 4.682% |  | 5.0942
BRUNSWICK 11041020 | 152481104 | BRUNSWICK 1104 | Nevada | 524 | 4.691% |  | 28.7064
CLARK ROAD 11022068 | 103091102 | CLARK ROAD 1102 | Butte | 525 | 4.7% |  | 11.0914
WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | Butte | 526 | 4.709% | Hybrid | 26.9664
GIRVAN 1101CB | 103401101 | GIRVAN 1101 | Shasta | 527 | 4.718% | Hybrid | 3.2748
PASO ROBLES 1104R56 | 182611104 | PASO ROBLES 1104 | San Luis Obispo | 528 | 4.727% |  | 12.4436
CAMP EVERS 210510214 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 529 | 4.736% |  | 2.2219
PINE GROVE 110235576 | 163751102 | PINE GROVE 1102 | Amador | 530 | 4.745% |  | 7.8751
MARIPOSA 210110070 | 254452101 | MARIPOSA 2101 | Mariposa | 531 | 4.754% |  | 25.7417
LUCERNE 110638632 | 43351106 | LUCERNE 1106 | Lake | 532 | 4.763% |  | 4.6558
HIGGINS 1104324510 | 152691104 | HIGGINS 1104 | Nevada | 533 | 4.772% |  | 12.4416
CALISTOGA 1102769230 | 42711102 | CALISTOGA 1102 | Napa | 534 | 4.781% | OH | 16.549
DIAMOND SPRINGS 1106930190 | 152261106 | DIAMOND SPRINGS 1106 | El Dorado | 535 | 4.79% | LR | 18.1945
RACETRACK 1704CB | 163761704 | RACETRACK 1704 | Tuolumne | 536 | 4.799% |  | 22.431
CLOVERDALE 1102429006 | 42821102 | CLOVERDALE 1102 | Sonoma | 537 | 4.808% |  | 1.9585
MOUNTAIN QUARRIES 210151584 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 538 | 4.816% |  | 21.8671
PIT NO 5 11011618 | 101321101 | PIT NO 5 1101 | Shasta | 539 | 4.825% |  | 6.1596
PUEBLO 2102943820 | 43292102 | PUEBLO 2102 | Napa | 540 | 4.834% |  | 2.4801
MARIPOSA 21021960 | 254452102 | MARIPOSA 2102 | Mariposa | 541 | 4.843% |  | 24.1642
CALPINE 1146400 | 48011146 | CALPINE 1146 | Sonoma | 543 | 4.861% |  | 1.8423
CAMP EVERS 210660120 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 544 | 4.87% |  | 4.2802
GIRVAN 11021028 | 103401102 | GIRVAN 1102 | Shasta | 545 | 4.879% |  | 17.753
CAMP EVERS 210510294 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 546 | 4.888% | UG | 8.3678
PINE GROVE 1102269286 | 163751102 | PINE GROVE 1102 | Amador | 548 | 4.906% |  | 28.1464
PIT NO 7 1101CB | 103501101 | PIT NO 7 1101 | Shasta | 549 | 4.915% | LR | 2.8406 |  | 2027
BEAR VALLEY 2105454432 | 252192105 | BEAR VALLEY 2105 | Mariposa | 550 | 4.924% | LR | 13.9808
TEMPLETON 2111A66 | 183052111 | TEMPLETON 2111 | San Luis Obispo | 551 | 4.933% |  | 34.0519
TASSAJARA 2112676362 | 14662112 | TASSAJARA 2112 | Contra Costa | 552 | 4.942% |  | 3.0421
UKIAH 1114408 | 42771114 | UKIAH 1114 | Mendocino | 553 | 4.951% |  | 38.1194
UKIAH 1111807988 | 42771111 | UKIAH 1111 | Mendocino | 554 | 4.96% |  | 4.1426
SILVERADO 2105131568 | 43432105 | SILVERADO 2105 | Napa | 556 | 4.978% | OH | 4.8943
CURTIS 170384944 | 163351703 | CURTIS 1703 | Tuolumne | 557 | 4.987% | Hybrid | 57.355
PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | Amador | 558 | 4.996% | Hybrid | 17.0253
HIGGINS 11032194 | 152691103 | HIGGINS 1103 | Nevada | 560 | 5.013% |  | 2.7524
POTTER VALLEY P H 110576498 | 42281105 | POTTER VALLEY P H 1105 | Mendocino | 561 | 5.022% |  | 6.2878
ALLEGHANY 1101183068 | 152101101 | ALLEGHANY 1101 | Sierra | 563 | 5.04% |  | 3.3692
MARIPOSA 2101309438 | 254452101 | MARIPOSA 2101 | Mariposa | 565 | 5.058% |  | 8.0755
CALAVERAS CEMENT 1101CB | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 566 | 5.067% | LR | 18.3839
SARATOGA 1107LC12 | 83371107 | SARATOGA 1107 | Santa Clara | 567 | 5.076% |  | 7.3435
CHOLAME 21025597 | 182562102 | CHOLAME 2102 | Monterey | 568 | 5.085% |  | 4.8632
AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | Fresno | 569 | 5.094% | Hybrid | 44.8682
OAKHURST 110310190 | 254421103 | OAKHURST 1103 | Madera | 570 | 5.103% |  | 8.3751
KIRKER 2104442850 | 14452104 | KIRKER 2104 | Contra Costa | 571 | 5.112% | Hybrid | 5.6891
IGNACIO 11051943 | 42481105 | IGNACIO 1105 | Marin | 572 | 5.121% |  | 1.2084
POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | Mendocino | 573 | 5.13% | Hybrid | 40.2546
OAKHURST 1103719490 | 254421103 | OAKHURST 1103 | Madera | 574 | 5.139% |  | 2.9793
BIG MEADOWS 21012248 | 102812101 | BIG MEADOWS 2101 | Plumas | 575 | 5.148% | UG | 9.2087
PINE GROVE 110283098 | 163751102 | PINE GROVE 1102 | Amador | 576 | 5.157% |  | 7.9157
SILVERADO 2103507513 | 43432103 | SILVERADO 2103 | Napa | 577 | 5.166% |  | 5.0603
MORGAN HILL 2111919856 | 83242111 | MORGAN HILL 2111 | Santa Clara | 578 | 5.175% |  | 9.3769
FROGTOWN 17027134 | 163451702 | FROGTOWN 1702 | Calaveras | 579 | 5.184% | LR | 22.9184
AUBERRY 1101R2838 | 254151101 | AUBERRY 1101 | Fresno | 580 | 5.192% |  | 20.5038
DOBBINS 110191464 | 153741101 | DOBBINS 1101 | Yuba | 581 | 5.201% |  | 7.0186
HIGHLANDS 11031282 | 43361103 | HIGHLANDS 1103 | Lake | 582 | 5.21% | LR | 8.0146
CEDAR CREEK 1101CB | 103321101 | CEDAR CREEK 1101 | Shasta | 583 | 5.219% |  | 48.5242
CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | Shasta | 584 | 5.228% |  | 29.3637
BEAR VALLEY 210190550 | 252192101 | BEAR VALLEY 2101 | Mariposa | 585 | 5.237% |  | 8.0911
PUEBLO 1105637242 | 43291105 | PUEBLO 1105 | Napa | 586 | 5.246% | Hybrid | 21.9074
ORO FINO 11022096 | 103031102 | ORO FINO 1102 | Butte | 587 | 5.255% |  | 13.9689
UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | Lake | 588 | 5.264% | OH | 1.0869
CALISTOGA 1101843761 | 42711101 | CALISTOGA 1101 | Napa | 589 | 5.273% |  | 4.1326
DUNLAP 11027360 | 254061102 | DUNLAP 1102 | Fresno | 590 | 5.282% |  | 8.9415
OAKHURST 1102683678 | 254421102 | OAKHURST 1102 | Madera | 591 | 5.291% |  | 8.1618
CLOVERDALE 1102674 | 42821102 | CLOVERDALE 1102 | Sonoma | 592 | 5.3% |  | 20.2103
DUNLAP 1103CB | 254061103 | DUNLAP 1103 | Fresno | 593 | 5.309% |  | 5.5101
HARTLEY 1101789752 | 43211101 | HARTLEY 1101 | Lake | 595 | 5.327% |  | 4.1528
ELK CREEK 110137334 | 102781101 | ELK CREEK 1101 | Glenn | 597 | 5.345% | LR | 9.4194
PIT NO 3 21011386 | 103732101 | PIT NO 3 2101 | Shasta | 598 | 5.354% |  | 6.7694
CHALLENGE 1101CB | 103201101 | CHALLENGE 1101 | Yuba | 599 | 5.363% |  | 16.4398
CAMP EVERS 2105426822 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 601 | 5.38% |  | 1.1372
WEIMAR 1102CB | 152491102 | WEIMAR 1102 | Placer | 602 | 5.389% |  | 14.9283
SAN JOAQUIN #3 1101673480 | 252531101 | SAN JOAQUIN #3 1101 | Madera | 604 | 5.407% |  | 12.5405
CLARKSVILLE 210419772 | 153612104 | CLARKSVILLE 2104 | El Dorado | 605 | 5.416% |  | 18.1334
FROGTOWN 17016807 | 163451701 | FROGTOWN 1701 | Calaveras | 608 | 5.443% | LR | 4.9864
PANOCHE 11034008 | 253671103 | PANOCHE 1103 | Fresno | 609 | 5.452% |  | 35.1601
CURTIS 170411300 | 163351704 | CURTIS 1704 | Tuolumne | 610 | 5.461% |  | 3.5255
LOS GATOS 1108LB86 | 82021108 | LOS GATOS 1108 | Santa Clara | 611 | 5.47% |  | 5.4015
OILFIELDS 1103N48 | 182391103 | OILFIELDS 1103 | Monterey | 612 | 5.479% |  | 47.5257
CALAVERAS CEMENT 1101585 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 613 | 5.488% |  | 14.1242
AUBERRY 1101R2839 | 254151101 | AUBERRY 1101 | Fresno | 614 | 5.497% |  | 12.5465
CORNING 110164090 | 103331101 | CORNING 1101 | Tehama | 615 | 5.506% | LR | 13.6417
MONTICELLO 1101130412 | 43051101 | MONTICELLO 1101 | Napa | 616 | 5.515% | OH | 3.8729
ALTO 11243121 | 42031124 | ALTO 1124 | Marin | 617 | 5.524% |  | 2.7541
OAKHURST 1101636114 | 254421101 | OAKHURST 1101 | Madera | 618 | 5.533% |  | 20.5595
SILVERADO 2104708 | 43432104 | SILVERADO 2104 | Napa | 619 | 5.542% | Hybrid | 4.9167
ALTO 1124430 | 42031124 | ALTO 1124 | Marin | 620 | 5.551% | UG | 7.0398
RED BLUFF 11041302 | 103541104 | RED BLUFF 1104 | Tehama | 621 | 5.56% |  | 14.529
SARATOGA 1105LC14 | 83371105 | SARATOGA 1105 | Santa Clara | 623 | 5.577% |  | 11.2464
EL DORADO PH 21016852 | 152762101 | EL DORADO PH 2101 | El Dorado | 625 | 5.595% |  | 25.0605
OREGON TRAIL 11031448 | 103521103 | OREGON TRAIL 1103 | Shasta | 626 | 5.604% |  | 30.6012
STAFFORD 11021048 | 43201102 | STAFFORD 1102 | Marin | 627 | 5.613% |  | 5.2099
SARATOGA 1107LC26 | 83371107 | SARATOGA 1107 | Santa Clara | 629 | 5.631% |  | 5.644
WILLITS 11032500 | 42661103 | WILLITS 1103 | Mendocino | 631 | 5.649% |  | 29.677
DUNBAR 110347964 | 43071103 | DUNBAR 1103 | Sonoma | 632 | 5.658% |  | 7.7118
HIGGINS 1103995672 | 152691103 | HIGGINS 1103 | Nevada | 633 | 5.667% |  | 5.8155
BEAR VALLEY 210110019 | 252192101 | BEAR VALLEY 2101 | Mariposa | 634 | 5.676% |  | 1.933
SAN LUIS OBISPO 1101V12 | 182631101 | SAN LUIS OBISPO 1101 | San Luis Obispo | 635 | 5.685% |  | 20.457
PIT NO 1 1101CB | 103721101 | PIT NO 1 1101 | Shasta | 636 | 5.694% |  | 6.6314
PUEBLO 1104580658 | 43291104 | PUEBLO 1104 | Napa | 637 | 5.703% |  | 10.2757
LAYTONVILLE 1101518 | 42681101 | LAYTONVILLE 1101 | Mendocino | 638 | 5.712% | Hybrid | 22.4154
HICKS 2101XR250 | 83432101 | HICKS 2101 | Santa Clara | 639 | 5.721% |  | 13.1469
BRUNSWICK 11052210 | 152481105 | BRUNSWICK 1105 | Nevada | 640 | 5.73% | LR | 24.6511
MORGAN HILL 2111XR398 | 83242111 | MORGAN HILL 2111 | Santa Clara | 641 | 5.739% |  | 29.2145
ATASCADERO 1101A02 | 182541101 | ATASCADERO 1101 | San Luis Obispo | 642 | 5.748% |  | 25.261
CALAVERAS CEMENT 110111236 | 162211101 | CALAVERAS CEMENT 1101 | Calaveras | 644 | 5.765% |  | 19.5866
CHOLAME 2102867686 | 182562102 | CHOLAME 2102 | Monterey | 645 | 5.774% |  | 25.2044
OILFIELDS 1103N62 | 182391103 | OILFIELDS 1103 | Monterey | 646 | 5.783% |  | 5.6723
LOS GATOS 110160052 | 82021101 | LOS GATOS 1101 | Santa Clara | 647 | 5.792% |  | 1.9053
WOODACRE 1102851 | 43021102 | WOODACRE 1102 | Marin | 648 | 5.801% | UG | 1.2608
OTTER 110263868 | 182941102 | OTTER 1102 | Monterey | 649 | 5.81% |  | 15.7816
OAKHURST 110310570 | 254421103 | OAKHURST 1103 | Madera | 651 | 5.828% | LR | 9.5969
ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | Sierra | 652 | 5.837% | Hybrid | 18.4885
CURTIS 170247488 | 163351702 | CURTIS 1702 | Tuolumne | 653 | 5.846% |  | 20.7078
CAMP EVERS 210533542 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 656 | 5.873% |  | 2.6586
ORO FINO 11012022 | 103031101 | ORO FINO 1101 | Butte | 657 | 5.882% |  | 16.1465
CURTIS 170210940 | 163351702 | CURTIS 1702 | Tuolumne | 658 | 5.891% |  | 10.5907
SUNOL 1101MR299 | 14241101 | SUNOL 1101 | Alameda | 659 | 5.9% |  | 4.9395
VOLTA 1102CB | 102541102 | VOLTA 1102 | Shasta | 660 | 5.909% | Hybrid | 3.3373
OILFIELDS 11032757 | 182391103 | OILFIELDS 1103 | Monterey | 661 | 5.918% |  | 2.4949
BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | Nevada | 662 | 5.927% | OH | 8.0109
HIGGINS 11041006 | 152691104 | HIGGINS 1104 | Nevada | 664 | 5.944% |  | 19.9813
SWIFT 2110XR254 | 83392110 | SWIFT 2110 | Santa Clara | 666 | 5.962% |  | 24.8051
DUNBAR 110379086 | 43071103 | DUNBAR 1103 | Sonoma | 667 | 5.971% |  | 6.7893
APPLE HILL 210297982 | 153662102 | APPLE HILL 2102 | El Dorado | 668 | 5.98% |  | 9.6784
ATASCADERO 1101A50 | 182541101 | ATASCADERO 1101 | San Luis Obispo | 669 | 5.989% |  | 21.7907
WYANDOTTE 11071510 | 102911107 | WYANDOTTE 1107 | Butte | 670 | 5.998% |  | 25.3115
DUNLAP 110239190 | 254061102 | DUNLAP 1102 | Fresno | 671 | 6.007% |  | 1.7106
CHOLAME 2102796386 | 182562102 | CHOLAME 2102 | Monterey | 672 | 6.016% | Hybrid | 39.8284
FULTON 1107145720 | 42561107 | FULTON 1107 | Sonoma | 674 | 6.034% |  | 10.2573
KING CITY 11037038 | 182031103 | KING CITY 1103 | Monterey | 675 | 6.043% |  | 22.0226
CURTIS 170539256 | 163351705 | CURTIS 1705 | Tuolumne | 676 | 6.052% |  | 26.17
AUBERRY 1101233716 | 254151101 | AUBERRY 1101 | Fresno | 677 | 6.061% | OH | 3.1838
CALPELLA 1101542 | 43411101 | CALPELLA 1101 | Mendocino | 678 | 6.07% |  | 33.2958
REDBUD 1101708166 | 43191101 | REDBUD 1101 | Lake | 679 | 6.079% | Hybrid | 11.7176
ALTO 1124432 | 42031124 | ALTO 1124 | Marin | 680 | 6.088% | UG | 7.7261
WEST POINT 1101L1969 | 163201101 | WEST POINT 1101 | Amador | 681 | 6.097% | UG | 1.099
CLOVERDALE 1101964556 | 42821101 | CLOVERDALE 1101 | Sonoma | 682 | 6.106% |  | 5.2094
SILVERADO 2102808 | 43432102 | SILVERADO 2102 | Napa | 683 | 6.115% |  | 5.5586
JESSUP 11012839 | 103441101 | JESSUP 1101 | Shasta | 687 | 6.15% |  | 1.4938
BRUNSWICK 1103173934 | 152481103 | BRUNSWICK 1103 | Nevada | 688 | 6.159% |  | 10.9398
LOS GATOS 1106LA42 | 82021106 | LOS GATOS 1106 | Santa Clara | 689 | 6.168% |  | 2.743
NARROWS 210248484 | 153132102 | NARROWS 2102 | Nevada | 690 | 6.177% |  | 41.8422
HIGHLANDS 1103520 | 43361103 | HIGHLANDS 1103 | Lake | 691 | 6.186% |  | 43.6096
AUBERRY 1101R2845 | 254151101 | AUBERRY 1101 | Fresno | 692 | 6.195% | Hybrid | 17.6672
WILDWOOD 110185112 | 103611101 | WILDWOOD 1101 | Trinity | 693 | 6.204% |  | 6.793
CORNING 110253184 | 103331102 | CORNING 1102 | Tehama | 694 | 6.213% | Hybrid | 31.8906
CLARK ROAD 11022582 | 103091102 | CLARK ROAD 1102 | Butte | 696 | 6.231% |  | 20.8663
LOS GATOS 1106LA46 | 82021106 | LOS GATOS 1106 | Santa Clara | 697 | 6.24% |  | 1.4934
HIGHLANDS 1102CB | 43361102 | HIGHLANDS 1102 | Lake | 698 | 6.249% | UG | 7.4912
CLOVERDALE 110184088 | 42821101 | CLOVERDALE 1101 | Sonoma | 699 | 6.258% |  | 17.4858
SARATOGA 1106340986 | 83371106 | SARATOGA 1106 | Santa Clara | 700 | 6.267% |  | 8.2903
OAKHURST 1103CB | 254421103 | OAKHURST 1103 | Madera | 701 | 6.276% |  | 33.4604
SALT SPRINGS 21011216 | 163692101 | SALT SPRINGS 2101 | Calaveras | 702 | 6.285% |  | 5.4808
ATASCADERO 1103492068 | 182541103 | ATASCADERO 1103 | San Luis Obispo | 703 | 6.294% |  | 5.6643
VOLTA 11011516 | 102541101 | VOLTA 1101 | Tehama | 704 | 6.303% | Hybrid | 25.8308 | 23.7245 | 2024
LOS GATOS 1106LA64 | 82021106 | LOS GATOS 1106 | Santa Clara | 705 | 6.312% |  | 12.6486
BIG BASIN 1101391980 | 82841101 | BIG BASIN 1101 | Santa Cruz | 706 | 6.321% |  | 5.0526
ALTO 11243745 | 42031124 | ALTO 1124 | Marin | 707 | 6.329% | UG | 4.4768
BRUNSWICK 110532536 | 152481105 | BRUNSWICK 1105 | Nevada | 708 | 6.338% | OH | 10.9898
MENLO 11028952 | 24131102 | MENLO 1102 | San Mateo | 709 | 6.347% |  | 3.3532
PUTAH CREEK 11028352 | 63681102 | PUTAH CREEK 1102 | Yolo | 712 | 6.374% | Hybrid | 11.8345
MIWUK 17029270 | 163661702 | MIWUK 1702 | Tuolumne | 713 | 6.383% |  | 5.7379
MARIPOSA 21029590 | 254452102 | MARIPOSA 2102 | Mariposa | 714 | 6.392% |  | 36.0398
HIGGINS 110332120 | 152691103 | HIGGINS 1103 | Nevada | 715 | 6.401% |  | 39.9809
HOPLAND 110194006 | 42251101 | HOPLAND 1101 | Mendocino | 716 | 6.41% |  | 15.4375
LAURELES 1111432 | 182371111 | LAURELES 1111 | Monterey | 717 | 6.419% |  | 48.9584
BRUNSWICK 11052140 | 152481105 | BRUNSWICK 1105 | Nevada | 718 | 6.428% |  | 34.2806
NARROWS 21022220 | 153132102 | NARROWS 2102 | Nevada | 719 | 6.437% |  | 28.4253
SHINGLE SPRINGS 210913322 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 721 | 6.455% |  | 40.9124
STELLING 1110568350 | 83481110 | STELLING 1110 | Santa Clara | 724 | 6.482% | Hybrid | 11.5215
MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | Mariposa | 725 | 6.491% | Hybrid | 4.7411
RESEARCH 2102183888 | 14692102 | RESEARCH 2102 | Contra Costa | 726 | 6.5% |  | 2.9991
MENDOCINO 110148750 | 42951101 | MENDOCINO 1101 | Mendocino | 727 | 6.509% |  | 18.122
JAMESON 1105466348 | 63801105 | JAMESON 1105 | Solano | 728 | 6.517% | Hybrid | 30.2294
STELLING 111060094 | 83481110 | STELLING 1110 | Santa Clara | 729 | 6.526% |  | 9.5997
DIAMOND SPRINGS 1106279670 | 152261106 | DIAMOND SPRINGS 1106 | El Dorado | 731 | 6.544% |  | 4.9272
DUNBAR 1103416 | 43071103 | DUNBAR 1103 | Sonoma | 732 | 6.553% |  | 2.7616
CLAYTON 2215812394 | 12022215 | CLAYTON 2215 | Contra Costa | 733 | 6.562% |  | 2.0742
AUBERRY 110149122 | 254151101 | AUBERRY 1101 | Fresno | 734 | 6.571% | OH | 11.3875
KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | Lake | 735 | 6.58% | Hybrid | 7.2213
CAMP EVERS 210660124 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 737 | 6.598% |  | 25.0618
ATASCADERO 1103440856 | 182541103 | ATASCADERO 1103 | San Luis Obispo | 738 | 6.607% |  | 35.176
PIT NO 5 11011606 | 101321101 | PIT NO 5 1101 | Shasta | 740 | 6.625% |  | 5.3571
PASO ROBLES 1103N50 | 182611103 | PASO ROBLES 1103 | San Luis Obispo | 742 | 6.643% | Hybrid | 1.8588
SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | San Luis Obispo | 743 | 6.652% | Hybrid | 8.483
NARROWS 21052748 | 153132105 | NARROWS 2105 | Nevada | 744 | 6.661% |  | 19.8731
COARSEGOLD 210210040 | 254432102 | COARSEGOLD 2102 | Madera | 745 | 6.67% |  | 20.5246
AUBERRY 1101R2579 | 254151101 | AUBERRY 1101 | Fresno | 746 | 6.679% |  | 34.2672
CLEAR LAKE 11011302 | 42141101 | CLEAR LAKE 1101 | Lake | 747 | 6.688% |  | 17.6725
SUNOL 1101MR387 | 14241101 | SUNOL 1101 | Alameda | 748 | 6.697% |  | 5.045
MC KEE 1107827486 | 83531107 | MC KEE 1107 | Santa Clara | 749 | 6.705% | LR | 2.9996
MORGAN HILL 2111419718 | 83242111 | MORGAN HILL 2111 | Santa Clara | 750 | 6.714% |  | 2.0969
BRUNSWICK 11032200 | 152481103 | BRUNSWICK 1103 | Nevada | 752 | 6.732% | OH | 5.5818
MORGAN HILL 2111XR292 | 83242111 | MORGAN HILL 2111 | Santa Clara | 753 | 6.741% |  | 12.0337
NARROWS 21022728 | 153132102 | NARROWS 2102 | Nevada | 756 | 6.768% |  | 19.3646
MIRABEL 110257840 | 42091102 | MIRABEL 1102 | Sonoma | 757 | 6.777% |  | 4.6775
BEAR VALLEY 2105916436 | 252192105 | BEAR VALLEY 2105 | Mariposa | 758 | 6.786% |  | 17.1506
OAKHURST 1102455174 | 254421102 | OAKHURST 1102 | Madera | 760 | 6.804% |  | 2.3577
MIWUK 1701360164 | 163661701 | MIWUK 1701 | Tuolumne | 761 | 6.813% |  | 6.9025
DOBBINS 110183186 | 153741101 | DOBBINS 1101 | Yuba | 762 | 6.822% |  | 7.3225
HOPLAND 1101960 | 42251101 | HOPLAND 1101 | Mendocino | 763 | 6.831% |  | 13.6393
VASCO 1102546328 | 13751102 | VASCO 1102 | Alameda | 764 | 6.84% |  | 42.1012
WILLITS 1103538 | 42661103 | WILLITS 1103 | Mendocino | 765 | 6.849% | LR | 6.3232
CURTIS 17046060 | 163351704 | CURTIS 1704 | Tuolumne | 766 | 6.858% |  | 4.0007
EL DORADO PH 2102771208 | 152762102 | EL DORADO PH 2102 | El Dorado | 767 | 6.867% |  | 4.2927
VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | Solano | 768 | 6.876% | Hybrid | 20.8491
CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | Napa | 769 | 6.885% | OH | 11.967
TEMPLETON 2110941946 | 183052110 | TEMPLETON 2110 | San Luis Obispo | 770 | 6.893% |  | 31.8098
PASO ROBLES 1103N58 | 182611103 | PASO ROBLES 1103 | San Luis Obispo | 771 | 6.902% | OH | 10.2436
WOODSIDE 11043583 | 24251104 | WOODSIDE 1104 | San Mateo | 772 | 6.911% |  | 2.7983
KONOCTI 11024300 | 43311102 | KONOCTI 1102 | Lake | 773 | 6.92% |  | 27.133
WOODSIDE 11018884 | 24251101 | WOODSIDE 1101 | San Mateo | 774 | 6.929% |  | 7.4686
DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | El Dorado | 775 | 6.938% |  | 38.8553
SARATOGA 1107413816 | 83371107 | SARATOGA 1107 | Santa Clara | 776 | 6.947% |  | 1.6265
OLETA 11022642 | 163541102 | OLETA 1102 | Amador | 777 | 6.956% |  | 4.6558
CAMP EVERS 21055232 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 778 | 6.965% |  | 4.4967
RINCON 1101146053 | 43321101 | RINCON 1101 | Sonoma | 779 | 6.974% | OH | 18.3449
EL DORADO PH 21026645 | 152762102 | EL DORADO PH 2102 | El Dorado | 780 | 6.983% |  | 4.0873
LAURELES 111110141 | 182371111 | LAURELES 1111 | Monterey | 781 | 6.992% |  | 2.8669
SISQUOC 1103858898 | 182811103 | SISQUOC 1103 | Santa Barbara | 782 | 7.001% |  | 19.5963
GANSNER 11012424 | 103021101 | GANSNER 1101 | Plumas | 785 | 7.028% | Hybrid | 18.6545
CHALLENGE 11021064 | 103201102 | CHALLENGE 1102 | Yuba | 786 | 7.037% |  | 19.5837
COARSEGOLD 210210330 | 254432102 | COARSEGOLD 2102 | Madera | 787 | 7.046% |  | 9.7643
MORAGA 1101CB | 13801101 | MORAGA 1101 | Contra Costa | 788 | 7.055% |  | 9.6612
CAMP EVERS 210574170 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 789 | 7.064% |  | 3.5962
DIAMOND SPRINGS 110518935 | 152261105 | DIAMOND SPRINGS 1105 | El Dorado | 790 | 7.073% |  | 6.4696
SAND CREEK 11037070 | 254601103 | SAND CREEK 1103 | Fresno | 791 | 7.081% |  | 17.0866
OTTER 11022166 | 182941102 | OTTER 1102 | Monterey | 794 | 7.108% |  | 4.0307
KONOCTI 1102716 | 43311102 | KONOCTI 1102 | Lake | 795 | 7.117% |  | 17.1034
JESSUP 110168362 | 103441101 | JESSUP 1101 | Shasta | 796 | 7.126% | Hybrid | 7.3033
CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 797 | 7.135% | OH | 11.9072
WILLITS 110337506 | 42661103 | WILLITS 1103 | Mendocino | 798 | 7.144% |  | 11.2077
SAN RAFAEL 11071166 | 42011107 | SAN RAFAEL 1107 | Marin | 799 | 7.153% |  | 15.0348
CURTIS 1702CB | 163351702 | CURTIS 1702 | Tuolumne | 800 | 7.162% |  | 22.7742
ELK CREEK 11012008 | 102781101 | ELK CREEK 1101 | Glenn | 801 | 7.171% |  | 18.0722
MENLO 11031721 | 24131103 | MENLO 1103 | San Mateo | 803 | 7.189% |  | 7.0953
TEMPLETON 2111R86 | 183052111 | TEMPLETON 2111 | San Luis Obispo | 804 | 7.198% |  | 14.3097
SILVERADO 2104806 | 43432104 | SILVERADO 2104 | Napa | 805 | 7.207% |  | 34.066
CORNING 110185162 | 103331101 | CORNING 1101 | Tehama | 806 | 7.216% |  | 5.7586
SARATOGA 1103LC16 | 83371103 | SARATOGA 1103 | Santa Clara | 807 | 7.225% |  | 5.1324
SOLEDAD 2102858388 | 182052102 | SOLEDAD 2102 | Monterey | 808 | 7.234% |  | 8.2144
TEMPLETON 2110N32 | 183052110 | TEMPLETON 2110 | San Luis Obispo | 811 | 7.261% |  | 28.5956
DIAMOND SPRINGS 110699658 | 152261106 | DIAMOND SPRINGS 1106 | El Dorado | 812 | 7.269% |  | 7.1074
SOLEDAD 2101107872 | 182052101 | SOLEDAD 2101 | Monterey | 813 | 7.278% |  | 12.14
ELECTRA 1101175840 | 162161101 | ELECTRA 1101 | Amador | 815 | 7.296% |  | 8.4314
NAPA 1112850068 | 42021112 | NAPA 1112 | Napa | 816 | 7.305% |  | 11.2426
LOS GATOS 110660116 | 82021106 | LOS GATOS 1106 | Santa Clara | 817 | 7.314% |  | 12.1344
HIGGINS 111051794 | 152691110 | HIGGINS 1110 | Nevada | 818 | 7.323% |  | 3.9671
LAYTONVILLE 110237586 | 42681102 | LAYTONVILLE 1102 | Mendocino | 819 | 7.332% |  | 13.895
SALT SPRINGS 210237300 | 163692102 | SALT SPRINGS 2102 | Calaveras | 820 | 7.341% |  | 6.9165
AUBERRY 1101323028 | 254151101 | AUBERRY 1101 | Fresno | 822 | 7.359% |  | 4.9842
REDBUD 1102922 | 43191102 | REDBUD 1102 | Lake | 823 | 7.368% |  | 7.7169
SAN JOAQUIN #2 1103CB | 252521103 | SAN JOAQUIN #2 1103 | Madera | 824 | 7.377% | OH | 67.8276
SARATOGA 1107167792 | 83371107 | SARATOGA 1107 | Santa Clara | 825 | 7.386% |  | 4.7512
DUNBAR 1102CB | 43071102 | DUNBAR 1102 | Sonoma | 826 | 7.395% |  | 8.5745
LAURELES 11112028 | 182371111 | LAURELES 1111 | Monterey | 827 | 7.404% |  | 8.7081
HARTLEY 110194178 | 43211101 | HARTLEY 1101 | Lake | 828 | 7.413% |  | 4.1213
POINT MORETTI 110139126 | 82931101 | POINT MORETTI 1101 | Santa Cruz | 830 | 7.431% |  | 4.8408
LOW GAP 11014086 | 192411101 | LOW GAP 1101 | Trinity | 833 | 7.457% |  | 11.5881
DOBBINS 11015202 | 153741101 | DOBBINS 1101 | Yuba | 834 | 7.466% | Hybrid | 17.2464
SPRING GAP 1702CB | 162831702 | SPRING GAP 1702 | Tuolumne | 835 | 7.475% |  | 7.3322
MIDDLETOWN 11021312 | 43141102 | MIDDLETOWN 1102 | Lake | 836 | 7.484% |  | 9.7943
LOS GATOS 1102526868 | 82021102 | LOS GATOS 1102 | Santa Clara | 837 | 7.493% |  | 1.2806
STILLWATER 11011320 | 103561101 | STILLWATER 1101 | Shasta | 838 | 7.502% |  | 19.8461
CLARKSVILLE 210413352 | 153612104 | CLARKSVILLE 2104 | El Dorado | 840 | 7.52% | Hybrid | 35.8073
MONTE RIO 1111140 | 42811111 | MONTE RIO 1111 | Sonoma | 841 | 7.529% | LR | 2.5925
MORGAN HILL 2105XR152 | 83242105 | MORGAN HILL 2105 | Santa Clara | 842 | 7.538% |  | 12.8017
HOLLISTER 21054018 | 182492105 | HOLLISTER 2105 | San Benito | 844 | 7.556% |  | 54.1493
MONTE RIO 11125040 | 42811112 | MONTE RIO 1112 | Sonoma | 846 | 7.574% |  | 5.8129
HIGHLANDS 1103568 | 43361103 | HIGHLANDS 1103 | Lake | 847 | 7.583% | LR | 9.1573
HIGGINS 1104CB | 152691104 | HIGGINS 1104 | Nevada | 848 | 7.592% |  | 11.9008
APPLE HILL 110313312 | 153661103 | APPLE HILL 1103 | El Dorado | 849 | 7.601% |  | 17.7135
CAMP EVERS 2106287578 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 850 | 7.61% |  | 4.3091
KONOCTI 11084039 | 43311108 | KONOCTI 1108 | Lake | 851 | 7.619% |  | 2.3141
PIERCY 2110XR258 | 83912110 | PIERCY 2110 | Santa Clara | 852 | 7.628% | LR | 26.322
SILVERADO 210437632 | 43432104 | SILVERADO 2104 | Napa | 853 | 7.637% | Hybrid | 7.4045
CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | Plumas | 854 | 7.645% | Hybrid | 6.4599
ALTO 1125510 | 42031125 | ALTO 1125 | Marin | 855 | 7.654% |  | 7.3727
PINE GROVE 11021765 | 163751102 | PINE GROVE 1102 | Amador | 856 | 7.663% |  | 1.4555
CURTIS 170268380 | 163351702 | CURTIS 1702 | Tuolumne | 857 | 7.672% |  | 8.453
BIG MEADOWS 2101CB | 102812101 | BIG MEADOWS 2101 | Plumas | 858 | 7.681% |  | 2.2107
CALPELLA 1101600 | 43411101 | CALPELLA 1101 | Mendocino | 859 | 7.69% |  | 24.4389
CURTIS 170463502 | 163351704 | CURTIS 1704 | Tuolumne | 860 | 7.699% |  | 10.5504
MOUNTAIN QUARRIES 21012504 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 861 | 7.708% |  | 25.1103
WOODACRE 1102CB | 43021102 | WOODACRE 1102 | Marin | 862 | 7.717% |  | 12.4595
KONOCTI 1102354890 | 43311102 | KONOCTI 1102 | Lake | 863 | 7.726% |  | 9.1017
OILFIELDS 110387034 | 182391103 | OILFIELDS 1103 | Monterey | 864 | 7.735% |  | 5.8779
SYCAMORE CREEK 1111976428 | 102971111 | SYCAMORE CREEK 1111 | Butte | 865 | 7.744% | Hybrid | 10.5355
MIWUK 1701953336 | 163661701 | MIWUK 1701 | Tuolumne | 866 | 7.753% | Hybrid | 11.6452
EL DORADO PH 210152456 | 152762101 | EL DORADO PH 2101 | El Dorado | 867 | 7.762% |  | 10.2621
LOS GATOS 1106LB48 | 82021106 | LOS GATOS 1106 | Santa Clara | 868 | 7.771% |  | 14.7043
GEYSERVILLE 110179788 | 42891101 | GEYSERVILLE 1101 | Sonoma | 870 | 7.789% |  | 41.6594
MARIPOSA 210110990 | 254452101 | MARIPOSA 2101 | Mariposa | 872 | 7.807% |  | 38.8218
MERCED FALLS 110287352 | 252811102 | MERCED FALLS 1102 | Mariposa | 876 | 7.842% |  | 26.3779
FELTON 0401CB | 83140401 | FELTON 0401 | N/A | 877 | 7.851% |  | 2.5372
OAKHURST 11035120 | 254421103 | OAKHURST 1103 | Madera | 878 | 7.86% | OH | 6.2338
LAYTONVILLE 1102CB | 42681102 | LAYTONVILLE 1102 | Mendocino | 879 | 7.869% |  | 12.9695
DUNLAP 11037040 | 254061103 | DUNLAP 1103 | Fresno | 881 | 7.887% |  | 25.4411
SHINGLE SPRINGS 210981390 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 882 | 7.896% |  | 18.4357
FROGTOWN 1701CB | 163451701 | FROGTOWN 1701 | Calaveras | 883 | 7.905% |  | 11.0963
LAS POSITAS 2108631066 | 14402108 | LAS POSITAS 2108 | Alameda | 884 | 7.914% |  | 7.1585
PLACERVILLE 1111508410 | 153081111 | PLACERVILLE 1111 | El Dorado | 885 | 7.923% |  | 5.0967
SHINGLE SPRINGS 210851476 | 153652108 | SHINGLE SPRINGS 2108 | El Dorado | 886 | 7.932% | LR | 6.5394
CAMP EVERS 210510786 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 888 | 7.95% |  | 4.4699
CEDAR CREEK 11011656 | 103321101 | CEDAR CREEK 1101 | Shasta | 889 | 7.959% |  | 31.9505
KANAKA 110165606 | 103221101 | KANAKA 1101 | Butte | 890 | 7.968% |  | 12.7484
MENLO 1103866118 | 24131103 | MENLO 1103 | San Mateo | 891 | 7.977% |  | 13.7345
CRESCENT MILLS 2101CB | 103132101 | CRESCENT MILLS 2101 | Plumas | 892 | 7.986% |  | 6.7994
SARATOGA 11075696 | 83371107 | SARATOGA 1107 | Santa Clara | 893 | 7.995% |  | 6.2446
CASTRO VALLEY 111010315 | 14091110 | CASTRO VALLEY 1110 | Alameda | 894 | 8.004% |  | 5.403
WOODSIDE 110147872 | 24251101 | WOODSIDE 1101 | San Mateo | 895 | 8.013% |  | 4.7418
CAMP EVERS 2106478670 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 896 | 8.021% |  | 2.8069
BIG BASIN 110212758 | 82841102 | BIG BASIN 1102 | Santa Cruz | 897 | 8.03% | Hybrid | 5.8734
LAURELES 11116421 | 182371111 | LAURELES 1111 | Monterey | 898 | 8.039% |  | 1.7275
LUCERNE 110638436 | 43351106 | LUCERNE 1106 | Lake | 899 | 8.048% |  | 4.7494
CAMP EVERS 2106130936 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 900 | 8.057% |  | 2.51
RAWSON 1103428534 | 103531103 | RAWSON 1103 | Tehama | 902 | 8.075% |  | 5.435
POINT MORETTI 110110726 | 82931101 | POINT MORETTI 1101 | Santa Cruz | 903 | 8.084% |  | 10.4869
LOS GATOS 1106917258 | 82021106 | LOS GATOS 1106 | Santa Clara | 904 | 8.093% |  | 4.0824
SHINGLE SPRINGS 2105CB | 153652105 | SHINGLE SPRINGS 2105 | El Dorado | 905 | 8.102% |  | 18.9503
SAN JUSTO 11014002 | 183181101 | SAN JUSTO 1101 | San Benito | 906 | 8.111% |  | 18.6728
CAMP EVERS 210512590 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 907 | 8.12% |  | 5.4869
CLAYTON 2213167700 | 12022213 | CLAYTON 2213 | Contra Costa | 908 | 8.129% |  | 2.4874
WYANDOTTE 110213044 | 102911102 | WYANDOTTE 1102 | Butte | 909 | 8.138% |  | 6.0113
SAN RAFAEL 110839156 | 42011108 | SAN RAFAEL 1108 | Marin | 910 | 8.147% |  | 4.8189
CLOVERDALE 1102383183 | 42821102 | CLOVERDALE 1102 | Sonoma | 911 | 8.156% |  | 14.7748
OAKHURST 110110090 | 254421101 | OAKHURST 1101 | Madera | 913 | 8.174% |  | 43.8357
BEN LOMOND 0401CB | 83040401 | BEN LOMOND 0401 | Santa Cruz | 915 | 8.192% |  | 7.7092
OLETA 11021204 | 163541102 | OLETA 1102 | Amador | 916 | 8.201% |  | 28.9671
LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | Santa Clara | 917 | 8.209% | Hybrid | 15.5274
GRASS VALLEY 11031700 | 152031103 | GRASS VALLEY 1103 | Nevada | 918 | 8.218% |  | 21.7769
EMERALD LAKE 04028858 | 24080402 | EMERALD LAKE 0402 | San Mateo | 919 | 8.227% |  | 1.8845
CALISTOGA 1101890 | 42711101 | CALISTOGA 1101 | Napa | 920 | 8.236% |  | 9.0971
SONOMA 11045661 | 42721104 | SONOMA 1104 | Sonoma | 921 | 8.245% |  | 5.0119
SPRING GAP 17029690 | 162831702 | SPRING GAP 1702 | Tuolumne | 922 | 8.254% |  | 16.6921
FULTON 1107914380 | 42561107 | FULTON 1107 | Sonoma | 924 | 8.272% |  | 3.0401
FROGTOWN 1702812366 | 163451702 | FROGTOWN 1702 | Calaveras | 925 | 8.281% |  | 2.6833
NOTRE DAME 11042408 | 102041104 | NOTRE DAME 1104 | Butte | 926 | 8.29% |  | 5.5261
MIWUK 1702S2247 | 163661702 | MIWUK 1702 | Tuolumne | 927 | 8.299% | Hybrid | 1.5243
LOS GATOS 110760118 | 82021107 | LOS GATOS 1107 | Santa Clara | 929 | 8.317% |  | 18.6541
BEAR VALLEY 210110000 | 252192101 | BEAR VALLEY 2101 | Mariposa | 930 | 8.326% |  | 33.8533
LOW GAP 110137498 | 192411101 | LOW GAP 1101 | Trinity | 931 | 8.335% |  | 16.2342
CAMP EVERS 210610718 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 932 | 8.344% |  | 8.3427
CLARK ROAD 1102514690 | 103091102 | CLARK ROAD 1102 | Butte | 933 | 8.353% |  | 3.4101
JOLON 11027068 | 182981102 | JOLON 1102 | Monterey | 934 | 8.362% |  | 3.8089
MIDDLETOWN 1101829164 | 43141101 | MIDDLETOWN 1101 | Lake | 935 | 8.371% |  | 9.8853
POINT MORETTI 110136516 | 82931101 | POINT MORETTI 1101 | Santa Cruz | 937 | 8.389% |  | 3.9186
WILLOW CREEK 11032936 | 192171103 | WILLOW CREEK 1103 | Humboldt | 938 | 8.397% | UG | 32.6024
SAND CREEK 11037110 | 254601103 | SAND CREEK 1103 | Fresno | 939 | 8.406% |  | 18.5818
PASO ROBLES 1103N54 | 182611103 | PASO ROBLES 1103 | San Luis Obispo | 940 | 8.415% | Hybrid | 23.1579
SARATOGA 1106LC24 | 83371106 | SARATOGA 1106 | Santa Clara | 941 | 8.424% |  | 11.5296
CALISTOGA 110178734 | 42711101 | CALISTOGA 1101 | Napa | 942 | 8.433% |  | 11.0321
UPPER LAKE 1101472084 | 42871101 | UPPER LAKE 1101 | Lake | 944 | 8.451% |  | 7.3403
CURTIS 1703CB | 163351703 | CURTIS 1703 | Tuolumne | 946 | 8.469% |  | 11.1253
LOS GATOS 1101LB40 | 82021101 | LOS GATOS 1101 | Santa Clara | 947 | 8.478% |  | 9.337
PENRYN 1103604 | 152561103 | PENRYN 1103 | Placer | 949 | 8.496% |  | 26.6934
MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | El Dorado | 950 | 8.505% |  | 5.5274
MORAGA 1102CB | 13801102 | MORAGA 1102 | Contra Costa | 951 | 8.514% | Hybrid | 8.2428
COVELO 1101430286 | 43061101 | COVELO 1101 | Mendocino | 952 | 8.523% |  | 5.592
ALLEGHANY 1101808 | 152101101 | ALLEGHANY 1101 | Sierra | 953 | 8.532% |  | 6.1773
NARROWS 2105CB | 153132105 | NARROWS 2105 | Nevada | 954 | 8.541% |  | 35.9784
HOPLAND 1101154790 | 42251101 | HOPLAND 1101 | Mendocino | 956 | 8.559% |  | 15.261
OREGON TRAIL 11031500 | 103521103 | OREGON TRAIL 1103 | Shasta | 957 | 8.568% | LR | 25.927
MIWUK 17028130 | 163661702 | MIWUK 1702 | Tuolumne | 958 | 8.577% |  | 9.669
CLAYTON 2215W531R | 12022215 | CLAYTON 2215 | Contra Costa | 959 | 8.585% |  | 8.2819
COARSEGOLD 2102CB | 254432102 | COARSEGOLD 2102 | Madera | 960 | 8.594% |  | 14.0764
GEYSERVILLE 1102484 | 42891102 | GEYSERVILLE 1102 | Sonoma | 962 | 8.612% |  | 49.0571
WILLITS 1103409216 | 42661103 | WILLITS 1103 | Mendocino | 963 | 8.621% |  | 19.8451
LOS GATOS 110760092 | 82021107 | LOS GATOS 1107 | Santa Clara | 964 | 8.63% |  | 9.7198
BEN LOMOND 040116010 | 83040401 | BEN LOMOND 0401 | Santa Cruz | 965 | 8.639% |  | 1.6882
CAMP EVERS 21055146 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 966 | 8.648% |  | 5.9263
MONTE RIO 111264682 | 42811112 | MONTE RIO 1112 | Sonoma | 967 | 8.657% |  | 1.7722
BIG MEADOWS 21012510 | 102812101 | BIG MEADOWS 2101 | Plumas | 969 | 8.675% | UG | 8.6382
EAST QUINCY 1101186938 | 102551101 | EAST QUINCY 1101 | Plumas | 970 | 8.684% |  | 2.9866
LAURELES 11112020 | 182371111 | LAURELES 1111 | Monterey | 972 | 8.702% | OH | 33.9289
AUBERRY 1101D4982 | 254151101 | AUBERRY 1101 | Fresno | 975 | 8.729% |  | 2.6245
BIG BASIN 110169550 | 82841101 | BIG BASIN 1101 | Santa Cruz | 976 | 8.738% |  | 12.4742
MIRABEL 1102332 | 42091102 | MIRABEL 1102 | Sonoma | 977 | 8.747% |  | 6.9611
LOS GATOS 1101950286 | 82021101 | LOS GATOS 1101 | Santa Clara | 978 | 8.756% |  | 1.0346
SHINGLE SPRINGS 21107742 | 153652110 | SHINGLE SPRINGS 2110 | El Dorado | 979 | 8.765% |  | 23.1444
APPLE HILL 110412842 | 153661104 | APPLE HILL 1104 | El Dorado | 980 | 8.774% |  | 16.8588
WOODACRE 1102137662 | 43021102 | WOODACRE 1102 | Marin | 982 | 8.791% | UG | 8.6127
SCE TEHACHAPI 1101CB | 258131101 | SCE TEHACHAPI 1101 | Kern | 983 | 8.8% |  | 1.1708
SAN RAFAEL 1108322 | 42011108 | SAN RAFAEL 1108 | Marin | 984 | 8.809% | UG | 7.4326
SUNOL 1101MR297 | 14241101 | SUNOL 1101 | Alameda | 985 | 8.818% |  | 6.0926
POINT MORETTI 110136514 | 82931101 | POINT MORETTI 1101 | Santa Cruz | 986 | 8.827% |  | 6.8662
HICKS 111660050 | 83431116 | HICKS 1116 | Santa Clara | 988 | 8.845% |  | 8.169
LUCERNE 1106664 | 43351106 | LUCERNE 1106 | Lake | 989 | 8.854% |  | 11.1503
CAMP EVERS 210510728 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 990 | 8.863% |  | 11.5447
DUNLAP 11037080 | 254061103 | DUNLAP 1103 | Fresno | 991 | 8.872% |  | 10.7588
LAYTONVILLE 1101402 | 42681101 | LAYTONVILLE 1101 | Mendocino | 992 | 8.881% |  | 23.3671
HIGGINS 1104533648 | 152691104 | HIGGINS 1104 | Nevada | 993 | 8.89% |  | 6.7297
AUBURN 11028611 | 152161102 | AUBURN 1102 | Placer | 994 | 8.899% |  | 1.7982
PEORIA 170413490 | 163781704 | PEORIA 1704 | Calaveras | 995 | 8.908% |  | 5.42
CAMP EVERS 210510912 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 996 | 8.917% |  | 4.865
LOS GATOS 110760024 | 82021107 | LOS GATOS 1107 | Santa Clara | 997 | 8.926% |  | 3.7366
WILLOW CREEK 110347966 | 192171103 | WILLOW CREEK 1103 | Humboldt | 998 | 8.935% |  | 17.1146
BURNS 2101CB | 183582101 | BURNS 2101 | Santa Cruz | 999 | 8.944% |  | 1.666
PUEBLO 210378504 | 43292103 | PUEBLO 2103 | Napa | 1000 | 8.953% |  | 11.7489
SAN RAFAEL 1108516 | 42011108 | SAN RAFAEL 1108 | Marin | 1001 | 8.962% |  | 10.8191
LOS GATOS 1107812664 | 82021107 | LOS GATOS 1107 | Santa Clara | 1002 | 8.97% | UG | 8.188
LOS GATOS 1107772050 | 82021107 | LOS GATOS 1107 | Santa Clara | 1003 | 8.979% |  | 14.5035
MORGAN HILL 2105XR070 | 83242105 | MORGAN HILL 2105 | Santa Clara | 1006 | 9.006% |  | 8.6751
HIGHLANDS 1103CB | 43361103 | HIGHLANDS 1103 | Lake | 1007 | 9.015% |  | 12.2277
CLARK ROAD 1102407706 | 103091102 | CLARK ROAD 1102 | Butte | 1009 | 9.033% |  | 9.183
RISING RIVER 11019032 | 103551101 | RISING RIVER 1101 | Shasta | 1010 | 9.042% |  | 23.289
FROGTOWN 17021573 | 163451702 | FROGTOWN 1702 | Calaveras | 1011 | 9.051% |  | 17.9534
CALISTOGA 1101727772 | 42711101 | CALISTOGA 1101 | Napa | 1012 | 9.06% |  | 1.9315
OLETA 1101296804 | 163541101 | OLETA 1101 | Amador | 1013 | 9.069% |  | 3.3899
ELK CREEK 11012212 | 102781101 | ELK CREEK 1101 | Glenn | 1014 | 9.078% | LR | 33.6921
BIG BASIN 110112838 | 82841101 | BIG BASIN 1101 | Santa Cruz | 1015 | 9.087% |  | 2.3734
LOW GAP 11014160 | 192411101 | LOW GAP 1101 | Trinity | 1016 | 9.096% | OH | 17.385
DUNBAR 1103302 | 43071103 | DUNBAR 1103 | Sonoma | 1017 | 9.105% |  | 4.3767
CURTIS 1701CB | 163351701 | CURTIS 1701 | Tuolumne | 1018 | 9.114% | UG | 12.0898
KERCKHOFF 1101CB | 252561101 | KERCKHOFF 1101 | Fresno | 1019 | 9.123% |  | 16.6898
MIWUK 1702576504 | 163661702 | MIWUK 1702 | Tuolumne | 1020 | 9.132% |  | 4.0914
POINT MORETTI 11015078 | 82931101 | POINT MORETTI 1101 | Santa Cruz | 1021 | 9.141% |  | 14.8482
APPLE HILL 210277546 | 153662102 | APPLE HILL 2102 | El Dorado | 1022 | 9.15% |  | 42.3317
LONE TREE 2105708440 | 13232105 | LONE TREE 2105 | Contra Costa | 1023 | 9.158% |  | 15.9536
WYANDOTTE 110738438 | 102911107 | WYANDOTTE 1107 | Butte | 1024 | 9.167% |  | 16.6395
TEMPLETON 2110317796 | 183052110 | TEMPLETON 2110 | San Luis Obispo | 1025 | 9.176% | LR | 7.3781
WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | San Mateo | 1026 | 9.185% | OH | 13.1152
NARROWS 21052216 | 153132105 | NARROWS 2105 | Nevada | 1027 | 9.194% |  | 58.1749
CLARK ROAD 110281296 | 103091102 | CLARK ROAD 1102 | Butte | 1028 | 9.203% |  | 15.6241
SARATOGA 1115463510 | 83371115 | SARATOGA 1115 | Santa Clara | 1029 | 9.212% |  | 2.9744
CAMP EVERS 210612518 | 83622106 | CAMP EVERS 2106 | Santa Cruz | 1030 | 9.221% |  | 15.4984
POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | Kern | 1031 | 9.23% |  | 7.756
CAMP EVERS 210311056 | 83622103 | CAMP EVERS 2103 | Santa Cruz | 1032 | 9.239% |  | 4.1356
SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | Santa Barbara | 1033 | 9.248% | UG | 17.2354
FULTON 1107604 | 42561107 | FULTON 1107 | Sonoma | 1034 | 9.257% | OH | 4.2385
MONTE RIO 111164758 | 42811111 | MONTE RIO 1111 | Sonoma | 1035 | 9.266% | UG | 10.48
CAMP EVERS 2105601610 | 83622105 | CAMP EVERS 2105 | Santa Cruz | 1036 | 9.275% |  | 10.4054
CAYETANO 2109884904 | 14422109 | CAYETANO 2109 | Alameda | 1037 | 9.284% |  | 25.728
APPLE HILL 110412832 | 153661104 | APPLE HILL 1104 | El Dorado | 1039 | 9.302% |  | 18.7715
CURTIS 170565908 | 163351705 | CURTIS 1705 | Tuolumne | 1040 | 9.311% |  | 16.7731
SAN RAMON 210853732 | 14232108 | SAN RAMON 2108 | Contra Costa | 1041 | 9.32% |  | 7.6074
EL DORADO PH 210126000 | 152762101 | EL DORADO PH 2101 | El Dorado | 1042 | 9.329% | Hybrid | 3.6612
WYANDOTTE 1105601234 | 102911105 | WYANDOTTE 1105 | Butte | 1043 | 9.338% |  | 10.479
ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | Glenn | 1044 | 9.346% | Hybrid | 29.7516
PUTAH CREEK 110396792 | 63681103 | PUTAH CREEK 1103 | Yolo | 1045 | 9.355% |  | 4.8845
LAYTONVILLE 1102572 | 42681102 | LAYTONVILLE 1102 | Mendocino | 1046 | 9.364% |  | 15.843
HICKS 2103LB50 | 83432103 | HICKS 2103 | Santa Clara | 1047 | 9.373% |  | 10.9822
NORTH BRANCH 1101CB | 163231101 | NORTH BRANCH 1101 | Calaveras | 1048 | 9.382% |  | 20.3201
RADUM 1105806392 | 13151105 | RADUM 1105 | Alameda | 1049 | 9.391% |  | 5.3848
BANGOR 11017446 | 103191101 | BANGOR 1101 | Yuba | 1050 | 9.4% |  | 43.1608
MIDDLETOWN 1102878 | 43141102 | MIDDLETOWN 1102 | Lake | 1051 | 9.409% |  | 5.6332
MORGAN HILL 2105XR176 | 83242105 | MORGAN HILL 2105 | Santa Clara | 1052 | 9.418% |  | 27.3946
WEST POINT 110136674 | 163201101 | WEST POINT 1101 | Amador | 1053 | 9.427% |  | 11.6832
LAYTONVILLE 11011760 | 42681101 | LAYTONVILLE 1101 | Mendocino | 1054 | 9.436% | LR | 12.5889
DIAMOND SPRINGS 1104705100 | 152261104 | DIAMOND SPRINGS 1104 | El Dorado | 1055 | 9.445% |  | 8.2784
DUNLAP 11027849F | 254061102 | DUNLAP 1102 | Fresno | 1056 | 9.454% | Hybrid | 8.6069
UKIAH 1111534 | 42771111 | UKIAH 1111 | Mendocino | 1057 | 9.463% |  | 20.5975
BIG TREES 0402737512 | 83050402 | BIG TREES 0402 | N/A | 1058 | 9.472% |  | 6.838
PINE GROVE 1102467560 | 163751102 | PINE GROVE 1102 | Amador | 1059 | 9.481% |  | 2.0079
CURTIS 17019230 | 163351701 | CURTIS 1701 | Tuolumne | 1060 | 9.49% |  | 2.9616
FROGTOWN 1702737236 | 163451702 | FROGTOWN 1702 | Calaveras | 1061 | 9.499% |  | 26.6465
SHINGLE SPRINGS 21092679 | 153652109 | SHINGLE SPRINGS 2109 | El Dorado | 1062 | 9.508% |  | 6.9571
BOLINAS 1101806 | 42261101 | BOLINAS 1101 | Marin | 1063 | 9.517% |  | 3.089
SPANISH CREEK 4401CB | 103104401 | SPANISH CREEK 4401 | N/A | 1064 | 9.526% | Hybrid | 7.9437
SAN RAFAEL 11081210 | 42011108 | SAN RAFAEL 1108 | Marin | 1065 | 9.534% |  | 5.4847
MONTE RIO 1112CB | 42811112 | MONTE RIO 1112 | Sonoma | 1067 | 9.552% |  | 3.5251
SALT SPRINGS 21028442 | 163692102 | SALT SPRINGS 2102 | Calaveras | 1068 | 9.561% |  | 12.0784
UKIAH 1114206824 | 42771114 | UKIAH 1114 | Mendocino | 1070 | 9.579% |  | 16.9073
MONTE RIO 1111506 | 42811111 | MONTE RIO 1111 | Sonoma | 1071 | 9.588% |  | 1.2682
BUTTE 1105751990 | 103081105 | BUTTE 1105 | Butte | 1072 | 9.597% | OH | 1.8687
BIG BASIN 110276752 | 82841102 | BIG BASIN 1102 | Santa Cruz | 1074 | 9.615% |  | 2.6958
PINE GROVE 110152088 | 163751101 | PINE GROVE 1101 | Amador | 1075 | 9.624% |  | 2.4863
WHITMORE 11011594 | 103601101 | WHITMORE 1101 | Shasta | 1076 | 9.633% | LR | 24.0015
HIGGINS 1104498932 | 152691104 | HIGGINS 1104 | Nevada | 1077 | 9.642% |  | 4.1675
FROGTOWN 170212282 | 163451702 | FROGTOWN 1702 | Calaveras | 1079 | 9.66% |  | 6.4576
DUNBAR 1101440 | 43071101 | DUNBAR 1101 | Sonoma | 1080 | 9.669% | UG | 14.4489
VINEYARD 2108609690 | 14502108 | VINEYARD 2108 | Alameda | 1081 | 9.678% |  | 7.5157
OILFIELDS 1103N64 | 182391103 | OILFIELDS 1103 | Monterey | 1082 | 9.687% |  | 12.6078
FULTON 1107214 | 42561107 | FULTON 1107 | Sonoma | 1083 | 9.696% | Hybrid | 11.6396
PLACERVILLE 210619732 | 153082106 | PLACERVILLE 2106 | El Dorado | 1085 | 9.714% |  | 9.246
SONOMA 11033052 | 42721103 | SONOMA 1103 | Sonoma | 1086 | 9.722% |  | 15.6399
ATASCADERO 1103A16 | 182541103 | ATASCADERO 1103 | San Luis Obispo | 1087 | 9.731% | Hybrid | 20.1897
MENDOCINO 110137462 | 42951101 | MENDOCINO 1101 | Mendocino | 1088 | 9.74% |  | 4.8265
HOPLAND 1101558 | 42251101 | HOPLAND 1101 | Mendocino | 1090 | 9.758% |  | 9.2239
DUNBAR 1103234 | 43071103 | DUNBAR 1103 | Sonoma | 1091 | 9.767% |  | 11.62
CURTIS 170190120 | 163351701 | CURTIS 1701 | Tuolumne | 1092 | 9.776% |  | 5.1026
RACETRACK 17038120 | 163761703 | RACETRACK 1703 | Tuolumne | 1093 | 9.785% |  | 8.7115
SAN JOAQUIN #3 1102CB | 252531102 | SAN JOAQUIN #3 1102 | Madera | 1094 | 9.794% |  | 9.5798
AUBURN 1101173014 | 152161101 | AUBURN 1101 | Placer | 1096 | 9.812% |  | 3.3902
OILFIELDS 1103N44 | 182391103 | OILFIELDS 1103 | Monterey | 1097 | 9.821% |  | 18.007
PASO ROBLES 1104R12 | 182611104 | PASO ROBLES 1104 | San Luis Obispo | 1098 | 9.83% |  | 39.8499
KONOCTI 1108CB | 43311108 | KONOCTI 1108 | Lake | 1099 | 9.839% |  | 8.8634
RINCON 1103198 | 43321103 | RINCON 1103 | Sonoma | 1100 | 9.848% | OH | 6.3704
OTTER 11012052 | 182941101 | OTTER 1101 | Monterey | 1101 | 9.857% |  | 9.2176
BIG BASIN 1101393582 | 82841101 | BIG BASIN 1101 | Santa Cruz | 1102 | 9.866% |  | 5.6021
CHALLENGE 11021902 | 103201102 | CHALLENGE 1102 | Yuba | 1103 | 9.875% |  | 4.8702
DUNBAR 1102261774 | 43071102 | DUNBAR 1102 | Sonoma | 1104 | 9.884% |  | 13.4851
BIG BASIN 110110720 | 82841101 | BIG BASIN 1101 | Santa Cruz | 1105 | 9.893% | OH | 4.5212
HALF MOON BAY 1103825502 | 24101103 | HALF MOON BAY 1103 | San Mateo | 1107 | 9.91% |  | 1.452
SAN MIGUEL 1106605393 | 182661106 | SAN MIGUEL 1106 | Monterey | 1109 | 9.928% |  | 25.0234
LAYTONVILLE 1101448108 | 42681101 | LAYTONVILLE 1101 | Mendocino | 1110 | 9.937% |  | 7.1118
BIG TREES 04025300 | 83050402 | BIG TREES 0402 | N/A | 1111 | 9.946% |  | 9.7027
BIG BASIN 110212992 | 82841102 | BIG BASIN 1102 | Santa Cruz | 1112 | 9.955% |  | 14.9919
BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | Santa Cruz | 1113 | 9.964% | Hybrid | 14.4156
HIGHLANDS 1103828 | 43361103 | HIGHLANDS 1103 | Lake | 1114 | 9.973% |  | 10.534
DUNLAP 11027060 | 254061102 | DUNLAP 1102 | Fresno | 1115 | 9.982% |  | 18.0342
HALF MOON BAY 1103157944 | 24101103 | HALF MOON BAY 1103 | San Mateo | 1116 | 9.991% |  | 4.2767