## Q5
PG&E 2027 System Hardening Alternative Mitigation Analysis
prepared on 10/24/2025
|  |  | Alternative Mitigations | [5 empty] | Selected Mitigation Data
Circuit Segment ID | Selected Mitigation | HFTD Tier | Alt 1: UG Benefit Cost Ratio | Alt 1: UG Net Benefit | Alt 2: OH Benefit Cost Ratio | Alt 2: OH Net Benefit | Alt 3: Hybrid Benefit Cost Ratio | Alt 3: Hybrid Net Benefit | Decision Rationale | Miles - OH | Miles - UG | Miles - LR | Miles - Remote Grid / LEIP | Total Miles | Total Capital Cost ($M) | $M / Mile | Total Risk | Risk Reduction | Risk Reduction / Mile | Planned Operative Date | Residential Customers | Non-Residential Customers
APPLE HILL 1104814656 | HYBRID | Tier 2 & 3 | 1.5 | 60.74 | 2.7 | 81.43 | 2.08 | 93.23 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 1.17 | 31.83 | 0 | 0 | 33 | 90.85 | 2.753 | 193.0312 | 179.66 | 3.9158 | 2027 | 425 | 12
FRENCH GULCH 11011892 | HYBRID | Tier 2 | 3.6 | 41.9 | 8 | 33.61 | 6.14 | 35.32 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 2.34 | 0.56 | 0 | 0 | 2.9 | 5.099 | 1.7583 | 59.0708 | 42.19 | 13.2448 | 2027 | 2 | 1
DOBBINS 1101 CB | HYBRID | Tier 2 & 3 | 1.17 | 3.17 | 3.34 | 8.35 | 2.83 | 11.66 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 1.01 | 1.5 | 0.03 | 0 | 2.54 | 22.487 | 8.8531 | 19.2152 | 18.04 | 4.6929 | 2027 | 221 | 52
WEST POINT 1101CB | HYBRID | Tier 3 | 1.94 | 38.79 | 4.55 | 45.43 | 2.55 | 47.38 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 0.4 | 6.06 | 0 | 0 | 6.46 | 23.909 | 3.7011 | 84.5713 | 78.03 | 9.0139 | 2027 | 3 | 0
FRENCH GULCH 11022902 | HYBRID | Tier 2 | 1.35 | 28.48 | 2.25 | 43.96 | 2.43 | 49.97 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 5.96 | 1.4 | 0 | 0 | 7.36 | 26.219 | 3.5624 | 110.4574 | 85.01 | 10.7609 | 2027 | 0 | 6
CALISTOGA 110135588 | HYBRID | Tier 3 | 2.31 | 48.71 | 7.1 | 25.43 | 4.28 | 50.23 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 0.995 | 2.85 | 0.25 | 0 | 4.095 | 12.697 | 3.1006 | 85.8104 | 65.53 | 7.2283 | 2027 | 0 | 9
ORO FINO 11022236 | HYBRID | Tier 3 | 0.86 | -6.05 | 5.07 | 20.96 | 5.38 | 23.68 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 1.89 | 0.65 | 0 | 0 | 2.54 | 4.258 | 1.6764 | 38.9122 | 29.09 | 10.2795 | 2027 | 1 | 2
MIDDLETOWN 1101644756 | HYBRID | Tier 2 & 3 | 3.26 | 178.17 | 6.56 | 150.98 | 3.38 | 160.28 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 5.22 | 16.01 | 0.37 | 0 | 21.6 | 56.571 | 2.619 | 266.1448 | 227.63 | 8.2477 | 2027 | 135 | 25
CLOVERDALE 1102672 | HYBRID | Tier 2 & 3 | 2.9 | 214.65 | 6.46 | 186.72 | 6.17 | 190.47 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 20.13 | 1.32 | 0 | 0 | 21.45 | 26.876 | 1.253 | 332.7543 | 227.3 | 10.2993 | 2027 | 106 | 31
GUSTINE 1102999258 | HYBRID | HFRA | 2.33 | 55.58 | 5.66 | 59.32 | 24.47 | 92.96 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 0.28 | 0 | 0 | 6.92 | 7.2 | 3.4587 | 0.48037 | 99.8107 | 96.92 | 10.0083 | 2027 | 0 | 3
MADISON 1105995448 | OVERHEAD | Tier 2 | 7.29 | 3.69 | 30.22 | 3.24 | 30.22 | 3.24 | UG BCR<50% OH BCR; Hybrid =OH | 0.17216 | 0 | 0 | 0 | 0.17216 | 0.1911 | 1.11 | 4.3482 | 3.35 | 19.4587 | 2027 | 0 | 2
ALTO 1124432 | UNDERGROUND | Tier 3 | 2.27 | 48.37 | 4.07 | 47.53 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 10.3 | 0 | 0 | 10.3 | 42.501 | 4.1263 | 92.0746 | 86.45 | 8.3932 | 2027 | 463 | 10
TEJON 11023760 | OVERHEAD | Tier 2 | 2.3 | 42.09 | 5.49 | 45.83 | 5.49 | 45.83 | UG BCR<50% OH BCR; Hybrid =OH | 6.48 | 0 | 0 | 0 | 6.48 | 7.2 | 1.1111 | 72.8684 | 56.05 | 8.6497 | 2027 | 0 | 0
PIT NO 5 11011614 | OVERHEAD | Tier 2 | 1.19 | 3.44 | 3.8 | 11.85 | 1.44 | 6.16 | Hybrid BCR<50% OH BCR; Hybrid NB<OH NB | 1.84 | 0 | 0 | 0 | 1.84 | 3.008 | 1.6348 | 21.0984 | 16.08 | 10.9402 | 2027 | 0 | 0
CUYAMA 1103684566 | OVERHEAD | Tier 2 | 1.63 | 13.44 | 5.49 | 21.31 | 5.49 | 21.31 | UG BCR<50% OH BCR; UG NB<OH NB; Hybrid =OH | 2.59 | 0 | 0 | 0 | 2.59 | 3.353 | 1.2946 | 34.8856 | 26.05 | 10.0579 | 2027 | 0 | 6
BALCH NO 1 1101R372 | OVERHEAD | Tier 2 | 0.97 | -1.46 | 4.99 | 26.66 | 1.7 | 15.65 | Hybrid BCR<50% OH BCR; Hybrid NB<OH NB | 3.85 | 0 | 0 | 0 | 3.85 | 4.724 | 1.227 | 43.5789 | 33.35 | 9.8831 | 2027 | 0 | 0
MARIPOSA 2101752630 | OVERHEAD | Tier 2 & 3 | 2.13 | 98.7 | 4.71 | 111.3 | 2.87 | 99.31 | Hybrid NB<OH NB | 18.45 | 0 | 0 | 0 | 18.45 | 21 | 1.1382 | 189.9551 | 141.27 | 8.2629 | 2027 | 138 | 11
ALLEGHANY 1101804, SC 1101/2 | HYBRID | Tier 2 & 3 | 1.02 | 2.63 | 1.36 | 19.89 | 1.32 | 20.9 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 12.99 | 6.47 | 0 | 0 | 19.46 | 51.763 | 2.66 | 124.4563 | 86.02 | 3.8469 | 2027 | 346 | 37
MONTE RIO 1113320 | UNDERGROUND | Tier 3 | 2.16 | 18.45 | 3.39 | 18.18 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 4.7 | 0 | 0 | 4.7 | 17.42 | 3.7064 | 35.5397 | 34.41 | 7.3213 | 2027 | 140 | 3
STELLING 11109265 | UNDERGROUND | Tier 2 | 2.21 | 32.11 | 3.88 | 28.57 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 6.84 | 0 | 0 | 6.84 | 23.913 | 3.4961 | 63.4513 | 58.64 | 8.5731 | 2027 | 47 | 12
CALAVERAS CEMENT 1101544800 | HYBRID | Tier 2 | 1.58 | 73.06 | 4.36 | 116.25 | 3.91 | 116.34 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 20.48 | 3.38 | 0.94 | 0 | 24.8 | 30.316 | 1.2224 | 203.0718 | 156.33 | 6.0827 | 2027 | 107 | 10
ALTO 11243745 | UNDERGROUND | Tier 3 | 2.01 | 21.62 | 2.94 | 18.49 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 6.05 | 0 | 0 | 6.05 | 23.323 | 3.855 | 46.0572 | 42.98 | 7.1041 | 2027 | 180 | 7
PINE GROVE 110245292 | UNDERGROUND | Tier 2 & 3 | 3.72 | 72.63 | 3.34 | 48.69 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 11.79 | 0 | 0 | 11.79 | 32.238 | 2.7344 | 107.2306 | 99.32 | 8.4241 | 2027 | 458 | 21
SAN LUIS OBISPO 1104982992 | HYBRID | Tier 3 | 1.59 | 27.64 | 3.32 | 38.78 | 3 | 40.99 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 5.68 | 3.2 | 0 | 0 | 8.88 | 25.538 | 2.8759 | 74.5589 | 61.51 | 6.2477 | 2027 | 28 | 16
MONTICELLO 1101130412 | OVERHEAD | Tier 2 | 1.16 | 5.95 | 3.72 | 13.86 | 3.72 | 13.86 | UG BCR<50% OH BCR; UG NB<OH NB; Hybrid =OH | 3.13 | 0 | 0 | 0 | 3.13 | 3.6348 | 1.1613 | 42.9285 | 18.95 | 6.0543 | 2027 | 0 | 8
BONNIE NOOK 1102542186 | UNDERGROUND | Tier 3 | 2.77 | 27.16 | 3.4 | 20.55 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 5.49 | 0.3 | 0 | 5.79 | 14.669 | 2.5335 | 44.6062 | 42.54 | 7.3472 | 2027 | 82 | 8
SANTA YNEZ 1101980192 | OVERHEAD | Tier 3 | 1.71 | 17.47 | 4.03 | 19.85 | 2.83 | 19.14 | Hybrid NB<OH NB | 3.88 | 0 | 0 | 0 | 3.88 | 4.616 | 1.1897 | 42.4143 | 26.39 | 7.6237 | 2027 | 6 | 36
BUCKS CREEK 1103CB | HYBRID | Tier 3 | 0.58 | -3.66 | 3.22 | 2.11 | 3.35 | 2.63 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 0.41 | 0.12 | 0 | 0 | 0.53 | 0.87 | 1.6415 | 5.6574 | 3.75 | 5.7736 | 2027 | 8 | 9
PEORIA 1704877670 | OVERHEAD | Tier 2 | 1.56 | 19.83 | 4.29 | 32.38 | 4.29 | 32.38 | UG BCR<50% OH BCR; UG NB<OH NB; Hybrid =OH | 6.35 | 0 | 0 | 0 | 6.35 | 6.913 | 1.0887 | 55.392 | 42.21 | 6.6472 | 2027 | 6 | 9
BIG BEND 1101CB | HYBRID | Tier 3 | 1.87 | 97.55 | 2.97 | 72.6 | 2.17 | 88.72 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 1.14 | 22.47 | 0 | 0 | 23.61 | 75.743 | 3.2081 | 176.8998 | 164.22 | 4.6353 | 2027 | 106 | 8
FORT ROSS 112170288 | HYBRID | Tier 2 & 3 | 1.71 | 77.84 | 2.67 | 84.27 | 1.9 | 87.98 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 1.15 | 33.13 | 0 | 0 | 34.28 | 94.7056 | 2.7627 | 196.2423 | 185.5 | 3.9312 | 2027 | 120 | 20
CALAVERAS CEMENT 11011419 | HYBRID | Tier 2 | 1.64 | 45.43 | 3.41 | 59.38 | 2.7 | 60.47 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 9.6 | 5.54 | 0.18 | 0 | 15.32 | 28.405 | 1.8541 | 125.0423 | 95.97 | 5.4863 | 2027 | 128 | 13
ALLEGHANY 1101806 | HYBRID | Tier 3 | 0.91 | -8.02 | 2.2 | 34 | 2.29 | 38.75 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 7.794 | 3.8 | 0.03 | 0 | 11.624 | 23.679 | 2.0371 | 85.2618 | 68.86 | 5.3527 | 2027 | 66 | 10
MIWUK 17021808 | UNDERGROUND | Tier 3 | 2.62 | 11.62 | 3.4 | 7.27 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 2.51 | 0 | 0 | 2.51 | 8.244 | 3.2845 | 20.8688 | 18.81 | 7.494 | 2027 | 237 | 29
CORNING 110185152 | HYBRID | Tier 2 | 1.79 | 73.39 | 3.26 | 79.09 | 3.12 | 79.87 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 21.77 | 2.24 | 0 | 0 | 24.01 | 27.397 | 1.1411 | 171.394 | 117.53 | 4.753 | 2027 | 395 | 17
STELLING 1110568350 | HYBRID | Tier 2 & 3 | 0.71 | -38.79 | 2.46 | 40.01 | 2.26 | 40.76 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 4.9 | 6.74 | 0 | 0 | 11.64 | 24.05 | 2.0662 | 104.2228 | 73.21 | 5.7964 | 2027 | 60 | 7
SILVERADO 2104324994 | HYBRID | Tier 3 | 1.82 | 1.78 | 2.44 | 1.35 | 9.03 | 3.46 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 0 | 0.26 | 0.04 | 0.22 | 0.52 | 0.9616 | 1.8492 | 4.9967 | 3.89 | 4.4038 | 2027 | 48 | 5
COALINGA NO 2 11059260 | HYBRID | HFRA | 1.33 | 34.89 | 3.64 | 77.01 | 6.04 | 118.19 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 0 | 0 | 0 | 17.76 | 17.76 | 13.341 | 0.75118 | 147.2975 | 141.64 | 5.9758 | 2027 | 2 | 6
PLACERVILLE 2106CB | UNDERGROUND | Tier 2 & 3 | 2.47 | 51.17 | 2.87 | 33.15 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0.02 | 11.81 | 0 | 0 | 11.83 | 34.087 | 2.8814 | 129.8341 | 86.04 | 7.273 | 2027 | 722 | 42
PIKE CITY 1102CB | HYBRID | Tier 3 | 1.2 | 12.57 | 1.54 | 17.23 | 1.35 | 18.39 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 0 | 13.12 | 0 | 5.885 | 19.005 | 46.353 | 2.439 | 73.3503 | 70.54 | 2.5951 | 2027 | 12 | 8
SUNOL 1101298061 | HYBRID | Tier 2 & 3 | 1.57 | 12.53 | 2.61 | 15.36 | 2.41 | 17.31 | Hybrid BCR>1; Hybrid BCR >50% OH BCR; Hybrid NB>OH NB | 2.49 | 2.47 | 0 | 0 | 4.96 | 10.701 | 2.1575 | 35.5946 | 29.56 | 5.0222 | 2027 | 182 | 12
MOUNTAIN QUARRIES 21011130 | UNDERGROUND | Tier 2 & 3 | 2.3 | 82.88 | 3.23 | 71.63 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 28.11 | 0 | 0 | 28.11 | 75.306 | 2.679 | 153.3207 | 146.42 | 5.2088 | 2027 | 271 | 11
CALISTOGA 1101730666 | UNDERGROUND | Tier 2 & 3 | 1.97 | 7.19 | 3.13 | 6.43 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0.049 | 2.29 | 0 | 0 | 2.339 | 6.638 | 2.838 | 15.082 | 14.6 | 6.242 | 2027 | 2 | 2
NARROWS PH 1151CB | OVERHEAD | Tier 2 | 0.11 | -11.3 | 2.7 | 0.64 | 2.7 | 0.64 | UG BCR< 1; UG BCR<50% OH BCR; UG NB<OH NB; Hybrid =OH | 0.2 | 0 | 0 | 0 | 0.2 | 0.268 | 1.34 | 1.3445 | 1.02 | 5.1 | 2027 | 0 | 0
PIT NO 3 21011480 | UNDERGROUND | Tier 2 | 1.94 | 8.62 | 3.06 | 8.15 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0.02 | 2.65 | 0 | 0 | 2.67 | 9.255 | 3.4663 | 19.6974 | 17.8 | 6.6667 | 2027 | 0 | 5
SILVERADO 210478268 | UNDERGROUND | Tier 3 | 5.36 | 1.05 | 2.99 | 0.27 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 0.13 | 0 | 0 | 0.13 | 0.298 | 2.2923 | 1.3852 | 1.29 | 9.9231 | 2027 | 255 | 44
WISHON 1101514298 | OVERHEAD | Tier 2 & 3 | 0.96 | -1.65 | 2.13 | 15.93 | 1.77 | 13.53 | Hybrid NB<OH NB | 7.248 | 0 | 0.311 | 0 | 7.559 | 10.119 | 1.3387 | 39.4271 | 29.96 | 4.1024 | 2027 | 8 | 3
APPLE HILL 2102CB, 836878, 1532 | UNDERGROUND | Tier 2 & 3 | 1.11 | 19.26 | 0.47 | -54.12 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 55.43 | 0 | 0 | 55.43 | 158.071 | 2.8517 | 346.5029 | 189.73 | 3.4229 | 2027 | 1178 | 88
PIT NO 3 21011482 | UNDERGROUND | Tier 2 | 2.43 | 83.36 | 4.66 | 80.91 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 13.71 | 0 | 0 | 13.71 | 54.591 | 3.9818 | 146.6017 | 141.85 | 10.3465 | 2027 | 19 | 5
WEST POINT 110112256 | UNDERGROUND | Tier 3 | 2.63 | 25.09 | 1.99 | 12.55 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 5.95 | 0 | 0 | 5.95 | 20.062 | 3.3718 | 47.3151 | 40.5 | 6.8067 | 2027 | 435 | 8
WEST POINT 11014706 | UNDERGROUND | Tier 3 | 1.39 | 0.98 | 1.38 | 0.63 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 1.52 | 0 | 0 | 1.52 | 3.039 | 1.9993 | 4.0956 | 3.52 | 2.3158 | 2027 | 318 | 11
EL DORADO 2102CB | UNDERGROUND | Tier 3 | 3.99 | 18.16 | 2.39 | 6.76 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 3.98 | 0 | 0 | 3.98 | 7.464 | 1.8754 | 31.1121 | 24.25 | 6.093 | 2027 | 254 | 51
TEJON 1102732836 | UNDERGROUND | Tier 2 | 3.74 | 89.58 | 2.16 | 15.38 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 8.38 | 0 | 0 | 8.38 | 28.886 | 3.447 | 133.2927 | 122.23 | 14.5859 | 2027 | 179 | 89
FORESTHILL 11011802 | UNDERGROUND | Tier 3 | 3.18 | 109.26 | 1.66 | 32.68 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0.02 | 28.27 | 0 | 0 | 28.29 | 78.874 | 2.7881 | 183.9591 | 159.38 | 5.6338 | 2027 | 602 | 37
BONNIE NOOK 1102CB | UNDERGROUND | Tier 3 | 2.97 | 138.69 | 1.7 | 36.45 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 29.79 | 0 | 0 | 29.79 | 80.325 | 2.6964 | 240.5927 | 209.06 | 7.0178 | 2027 | 366 | 56
PUEBLO 2103678 | UNDERGROUND | Tier 2 & 3 | 1.84 | 124.16 | 2 | 54.58 | - | - | UG BCR>1; UG BCR >50% OH BCR; UG NB>OH NB | 0 | 48.85 | 0 | 0 | 48.85 | 142.3 | 2.913 | 298.5134 | 271.16 | 5.5509 | 2027 | 213 | 72
AUBERRY 110149122 | OVERHEAD | Tier 2 | 0.89 | -2.31 | 2.1 | 6.78 | 1.64 | 5.63 | Hybrid NB<OH NB | 4.14 | 0 | 0 | 0 | 4.14 | 4.3 | 1.0386 | 19.9262 | 12.94 | 3.4783 | 2027 | 67 | 5

## Definitions
Definitions
Circuit Segment ID | A | Identifies the segment of a circuit that will be hardened (a single subproject may span multiple circuit segments).
Selected Mitigation | B | The mitigation type selected based on the alternatives analysis
HFTD Tier | C | High Fire Threat District (HFTD) Tier Tier 2 - Areas where there is a higher risk (including likelihood and potential impacts on people and property) from utility related wildfires. Tier 3 - Areas where there is an extreme risk (including likelihood and potential impacts on people and property) from utility related wildfires. | Total Risk
APPLE HILL 1104814656
Alternative Mitigations |  | Information regarding each alternative scenario
DOBBINS 1101 CB | D-E | Undergrounding - project is 90% or more undergrounding and may include other mitigations that are less than 10% of the mileage of the project (overhead or line removal).
Alt 2: OH | F-G | Overhead Hardening - project is 90% or more overhead hardened and may include other mitigations that are less than 10% of the mileage of the project (undergrounding or line removal).
Alt 3: Hybrid | H-I | Any combination of UG, OH, and/or Removal.
Benefit Cost Ratio (BCR) | D,F,H | Present value of lifetime benefits divided by present value of lifetime costs
Net Benefit (NB) | E,G,I | Present value of lifetime benefits minus present value of lifetime costs
Decision Rationale |  | The outcome of the comparison between the alternative mitigations to justify the Selected Mitigation.
Hybrid BCR>1 & Hybrid BCR >50% OH BCR & Hybrid NB>OH NB | J | BCR of Hybrid is greater than 1 and BCR of Hybrid is greater than 50% of BCR of Overhead Hardening and NB of Hybrid is greater than NB of Overhead Hardening Results in Hybrid as the selected mitigation.
Hybrid BCR<50% OH BCR; Hybrid NB<OH NB |  | BCR of Hybrid is less than 50% of BCR of Overhead Hardening and NB of Hybrid is less than NB of Overhead Hardening Results in Overhead Hardening as the selected mitigation.
Hybrid NB<OH NB |  | NB of Hybrid is less than Net Benefit of Overhead Hardening Results in Overhead Hardening as the selected mitigation.
UG BCR< 1 & UG BCR<50% OH BCR & UG NB<OH NB & Hybrid =OH |  | BCR of Undergrounding is less than 1 and BCR of Undergrounding is less than 50% of BCR of Overhead Hardening and NB of Undergrounding is less then NB of Undergrounding and BCR & NB of Hybrid is equal to BCR & NB of Overhead Hardening Results in Overhead Hardening as the selected mitigation.
UG BCR>1 & UG BCR >50% OH BCR & UG NB>OH NB |  | BCR of Undergrounding is greater than 1 and BCR of Undergrounding is greater than 50% of BCR of Overhead Hardening and NB of Undergrounding is greater than NB of Overhead Hardening Results in Undergrounding as the selected mitigation.
UG BCR<50% OH BCR & UG NB<OH NB & Hybrid =OH |  | BCR of Undergrounding is less than 50% of BCR of Overhead Hardening and NB of Undergrounding is less than NB of Overhead Hardening and BCR & NB of Hybrid is equal to BCR & NB of Overhead Hardening Results in Overhead Hardening as the selected mitigation.
UG BCR<50% OH BCR & Hybrid =OH |  | BCR of Undergrounding is less than 50% of BCR of Overhead Hardening and BCR & NB of Hybrid is equal to BCR & NB of Overhead Hardening Results in Overhead Hardening as the selected mitigation.
Selected Mitigation Data |  | Information regarding the selected mitigation
Miles - UG | K | Miles of undergrounding estimated to take place as part of the selected solution
Miles - OH | L | Miles of overhead hardening estimated to take place as part of the selected solution
Miles - LR | M | Miles of line removal estimated to take place as part of the selected solution
Miles - Remote Grid / LEIP | N | Miles of line removal associated with Remote Grid or LEIP estimated to take place as part of the selected solution
Total Miles | O | Total miles of all mitigation methods estimated to take place as part of the selected solution
Total Capital Cost ($M) | P | Initial capital cost for selected solution (in millions of dollars)
$M / Mile | Q | Initial capital cost for selected solution (in millions of dollars) per mitigated mile installed
Total Risk | R | Net present value (NPV) of wildfire, reliability and public safety risk over lifetime (in millions of dollars)
Risk Reduction | S | Net present value (NPV) of mitigated wildfire, reliability and public safety risk over lifetime benefit (in millions of dollars) of the selected mitigation
Risk Reduction / Mile | T | Net present value (NPV) of mitigated wildfire, reliability and public safety risk over lifetime benefit (in millions of dollars) of the selected mitigation per mitigated mile installed
Planned Operative Date | U | The year that newly installed infrastructure is considered used and useful
Residential Customers | V | Sum of residential service point IDs on all circuit segments associated with this project
Non-Residential Customers | W | Sum of non-residential service point IDs on all circuit segments associated with this project
PLACERVILLE 2106CB
WEST POINT 110112256